## PMP
5 Process Groups
10 Knowledge Areas | Knowledge Area | Initiating - 2 | Planning - 24 | Executing - 10 | Monitoring and Controlling - 12 | Closing - 1
| Project Integration Management | Develop project charter | Develop project management plan | • Direct and manage the project work • Manage project knowledge | • Monitor and Control Project Work • Perform Integrated Change Control | Close project or phase
| Project Scope Management |  | • Plan scope management • Collect requirements • Create WBS |  | • Validate scope • Control scope
| Project Schedule Management |  | • Plan schedule management • Define activities • Sequence activities • Estimate activity durations • Develop schedule |  | Control schedule
| Project Cost Management |  | • Plan cost management • Estimate costs • Determine budget |  | Control costs
| Project Quality Management |  | Plan quality management | Manage quality | Control quality
| Project Resource Management |  | • Plan resource management • Estimate activity resources | • Acquire resources • Develop team • Manage team
| Project Communications Management |  | Plan communications management | Manage communications | Monitor communications
| Project Risk Management |  | • Plan risk management • Perform qualitative risk analysis • Perform quantitative risk analysis • Plan risk responses | Implement risk responses | Monitor risks
| Project Procurement Management |  | Plan procurement management | Conduct procurements | Control procurements
| Project Stakeholder Management | Identify stakeholders | Plan stakeholder engagement | Manage stakeholder engagement | Monitor stakeholder engagement

## Project Charter
Project Charter
Genral Project Information | CHARTER DATE: 05 May 2026
Project Name | e.g. Online Self Serve Payment System
Project Sponsor | The executive paying for the project, or giving resources.
Project manager | Vishvambruth Javagal
Expected Start Date | 2026-06-01
Expected Completed Date | 2026-12-31
Project Details
Project Description | High-level project description, purpose and reason "why" for the project.
Key Requirements | What is required to be delivered? Also written as "Features", a high-level list of what is required as an output of this project. e.g. The team will deliver these usable features in order: 1. Web page - working design 2. Online Payments 3. Back-end Integration
Expected Benefits | Enhanced customer ecperience providing access to an online channel for our customers, thereby personalising their channel of choice. Reduction in wait times for customers. Staff savings of around 9, 960 hours of effort each year. Increased Sales.
Estimated Cost & Resources | e.g. 35k costs including utilisation of internal delivery team and Subject Matter Experts
Estimated Milestones | Feature 1 - June 30 Feature 2 - July 30 Feature 3-September 10
Project Team (Resources) | Project Sponsor: Project Manager: Business Analysts: Developers: Test Lead: Subject Matter Experts:
Stakeholders (Impacted) | Name, Role Name, Role Department or area Team
Overall Project Risk | High level, what could go wrong? Risk, Likelihood, Impact Risk, Likelihood, Impact
Project Exit Criteria | Also "Success Criteria" e.g. Working, usable features released on time. What are the conditions to be met in order to close or to cancel the project or phase.

## Impact over Influence Chart
Stakeholder Map
|  | Project Name: | Enterprise CRM System Implementation
| # | Stakeholder Name | Role | Impact of Change | Level of Influence
| 1 | Sarah Johnson | Project Manager | 7 | 9
| 2 | Tom Williams | Product Owner | 6 | 8
| 3 | Michael Chen | Business Analyst | 8 | 5
| 4 | David Kumar | Solutions Architect | 6 | 7
| 5 | Emma Wilson | Database Developer | 9 | 3
| 6 | James Rodriguez | Backend Developer | 8 | 4
| 7 | Lisa Park | Frontend Developer | 8 | 3
| 8 | Robert Taylor | QA Lead | 7 | 5
| 9 | Anna Martinez | UAT Coordinator | 6 | 2
| 10 | Chris Brown | DevOps Engineer | 7 | 6
| 11 | Jennifer Lee | Training Lead | 5 | 3
| 12 | Kevin Zhang | Security Analyst | 4 | 6
| 13 | Rachel Green | Scrum Master | 3 | 4
| 14 | Maria Santos | Technical Writer | 2 | 1
| Chart Axis |  | 5 | 5
Impact over Influence Chart - Tutorial
What is an Impact over Influence Chart?
A stakeholder mapping tool that plots stakeholders based on how much they are IMPACTED by the project vs. how much INFLUENCE they have over decisions.
How to Read the Quadrants:
• High Impact, High Influence (Top-Right): Key players - Manage closely (e.g., PM, Product Owner)
• High Impact, Low Influence (Top-Left): Keep satisfied - Address concerns (e.g., Developers)
• Low Impact, High Influence (Bottom-Right): Keep informed - They influence but aren't impacted
• Low Impact, Low Influence (Bottom-Left): Monitor - Minimal engagement needed
💡 Tip: Update scores as the project evolves. Use this to prioritize communication strategies.

## Gantt Chart
GANTT CHART
Enterprise CRM System Implementation - Project Timeline
2026-06-08
| Project Start Date: | 2026-06-01 | [5 empty] | 2026-06-08 |  |  |  | 2026-07-06 |  |  |  |  | 2026-08-10 |  |  |  | 2026-09-07 |  |  |  |  | 2026-10-12 |  |  |  | 2026-11-09 |  |  |  | 2026-12-07 |  |  |  |  | 2027-01-11
| Project Name: | Enterprise CRM System Implementation |  |  |  |  | Week starting: | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25
# | Activity | Assigned To | Start | End | Days | Status | %Done
1 | Project Initiation & Planning | Sarah Johnson | 2026-05-04 | 2026-05-29 | 20 | Completed | 100%
2 | Requirements Gathering & Analysis | Michael Chen | 2026-06-01 | 2026-06-26 | 20 | Completed | 100% | bar: 2026-06-01 to 2027-01-25
3 | System Architecture Design | David Kumar | 2026-06-29 | 2026-07-24 | 20 | Completed | 100% | bar: 2026-06-01 to 2027-01-25
4 | Database Design & Development | Emma Wilson | 2026-07-27 | 2026-08-28 | 25 | Blocked | 20% | bar: 2026-06-01 to 2027-01-25
5 | Backend API Development | James Rodriguez | 2026-08-31 | 2026-10-02 | 25 | In progress | 40% | bar: 2026-06-01 to 2027-01-25
6 | Frontend UI Development | Lisa Park | 2026-10-05 | 2026-11-06 | 25 | In progress | 30% | bar: 2026-06-01 to 2027-01-25
7 | Integration & System Testing | Robert Taylor | 2026-11-09 | 2026-12-04 | 20 | Not started | 0% | bar: 2026-06-01 to 2027-01-25
8 | User Acceptance Testing (UAT) | Anna Martinez | 2026-12-07 | 2026-12-18 | 12 | Not started | 0% | bar: 2026-06-01 to 2027-01-25
9 | Deployment & Go-Live | Chris Brown | 2026-12-21 | 2026-12-25 | 5 | Not started | 0% | bar: 2026-06-01 to 2027-01-25
10 | Post Go-Live Support & Training | Jennifer Lee | 2026-12-28 | 2026-12-31 | 4 | Not started | 0% | bar: 2026-06-01 to 2027-01-25
Status
Not started
In progress
Blocked
Completed
What is a Gantt Chart?
A Gantt Chart is a visual project management tool that displays tasks or activities against time. Each task is represented as a horizontal bar, where: • The left edge shows when a task starts • The right edge shows when a task ends • The length of the bar represents the task duration • Colors often indicate task status (completed, in progress, blocked, not started) Gantt charts help project managers and teams see the entire project timeline at a glance, identify task dependencies, track progress, and ensure deadlines are met.
Formulas:
Days = IF(OR([Start]="",[End]=""),"", NETWORKDAYS([Start], [End]))

## RACI
RACI - Resource Assignment Matrix
|  | Project Name: | Enterprise CRM System Implementation |  |  |  | Project Manager: |  | Sarah Johnson
• R - Responsible - who performs the task • A - Accountable - who signs off • C - Consulted - who provides expert judgement • I - Informed - who is kept informed
Deliverables |  |  | Project Initiation & Planning | Requirements Gathering & Analysis | System Architecture Design | Database Design & Development | Backend API Development | Frontend UI Development | Integration & System Testing | User Acceptance Testing (UAT) | Deployment & Go-Live | Post Go-Live Support & Training
Name |  | Project Role
Sarah Johnson |  | Project Manager | A | A | A | A | A | A | A | A | A | A
Michael Chen |  | Business Analyst | C | R | C | I | I | I | C | R | I | C
David Kumar |  | Solutions Architect | C | C | R | C | C | C | I | I | I | I
Emma Wilson |  | Database Developer | I | C | C | R | C | I | C | I | I | I
James Rodriguez |  | Backend Developer | I | I | C | C | R | C | C | I | I | I
Lisa Park |  | Frontend Developer | I | I | C | I | C | R | C | I | I | I
Robert Taylor |  | QA Lead | I | C | C | C | C | C | R | C | I | I
Anna Martinez |  | UAT Coordinator | I | C | I | I | I | I | C | R | I | C
Chris Brown |  | DevOps Engineer | I | I | C | C | C | C | C | I | R | C
Jennifer Lee |  | Training Lead | I | C | I | I | I | I | I | C | C | R
Kevin Zhang |  | Security Analyst | C | C | C | C | C | C | C | C | C | I
Tom Williams |  | Product Owner | R | C | C | I | I | I | I | C | I | I
Rachel Green |  | Scrum Master | C | C | I | I | I | I | C | C | I | I
Maria Santos |  | Technical Writer | I | C | I | I | I | I | I | C | I | R
R | R - Responsible - who performs the task
A | A - Accountable - who signs off
C | C - Consulted - who provides expert judgement
I | I - who is kept informed
What is a RACI Matrix?
A RACI Matrix (also called a Responsibility Assignment Matrix) is a project management tool used to clarify roles and responsibilities for tasks and deliverables.
• R - Responsible: The person who performs the work to complete the task. There can be multiple people responsible.
• A - Accountable: The person who is ultimately answerable for the task's completion. There should be only ONE accountable person per task.
• C - Consulted: People who provide input and expertise before or during the task. Communication is two-way.
• I - Informed: People who need to be kept updated on progress or decisions. Communication is one-way.
Benefits: Eliminates confusion about roles, prevents tasks from falling through the cracks, ensures proper communication, and helps identify overloaded team members.
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on J6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on K6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on N6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on O6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable
Note on P6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Task or deliverable

## Risk Assessment
Risk Assessment
| Area Name: |  | Updated By |  |  |  | Date Last Updated: | 2026-05-31 |  |  |  | Risk Matricies | [6 empty] | Probability | Impact
[12 empty] | Risk Matrix | [6 empty] | Very High | Very High
|  |  |  | Inherent Risk (without controls) |  |  |  |  | Residual Risk (with controls) | [9 empty] | High | High
Unique ID | RISK Description | Caused by & Consequences | Risk Owners(s) Name and Role | Probability | Impact | Risk Rating | Control (s) | Contol Owner(s) Name and Role | Residual Probability | Residual Impact | Residual Risk Rating | Impact: |  | Very Low | Low | Medium | High | Very High | Medium | Medium
1 | Data Migration Failure | Caused by: Incompatible legacy data formats, corrupt data records, insufficient mapping Consequences: Data loss, system downtime, user frustration, compliance issues | Emma Wilson, Database Developer | High | Very High | Critical | Implement staged migration with validation checkpoints, create comprehensive data backup, use automated data cleansing tools | Emma Wilson, Database Developer | Medium | High | Severe | Probability | Very High | Moderate | Severe | Severe | Critical | Critical | Low | Low
2 | Scope Creep | Caused by: Unclear requirements, stakeholder pressure, lack of change control Consequences: Budget overrun, delayed delivery, team burnout, quality issues | Sarah Johnson, Project Manager | Very High | High | Critical | Establish formal change control process, define clear project boundaries, regular stakeholder alignment meetings | Sarah Johnson, Project Manager | Medium | Medium | Moderate |  | High | Sustainable | Moderate | Severe | Critical | Critical | Very Low | Very Low
3 | Integration Complexity with Legacy Systems | Caused by: Outdated APIs, poor documentation, vendor dependencies Consequences: Extended timelines, additional costs, functionality gaps | David Kumar, Solutions Architect | High | High | Critical | Early integration testing, engage vendor support, develop middleware adapters, maintain fallback options | James Rodriguez, Backend Developer | Low | Medium | Moderate |  | Medium | Sustainable | Moderate | Moderate | Severe | Critical
4 | Key Resource Unavailability | Caused by: Staff turnover, illness, competing priorities Consequences: Knowledge gaps, schedule delays, quality degradation | Sarah Johnson, Project Manager | Medium | High | Severe | Cross-training team members, document critical knowledge, maintain resource buffer, contractor standby list | Sarah Johnson, Project Manager | Low | Medium | Moderate |  | Low | Sustainable | Sustainable | Moderate | Severe | Critical
5 | User Adoption Resistance | Caused by: Poor change management, inadequate training, workflow disruption Consequences: Low system usage, workarounds, ROI impact, project failure | Jennifer Lee, Training Lead | High | Very High | Critical | Early user involvement, comprehensive training program, change champions network, phased rollout | Jennifer Lee, Training Lead | Medium | Medium | Moderate |  | Very Low | Sustainable | Sustainable | Sustainable | Moderate | Severe
6 | Security Vulnerabilities | Caused by: Inadequate security testing, new attack vectors, compliance gaps Consequences: Data breach, regulatory fines, reputation damage, legal liability | Kevin Zhang, Security Analyst | Medium | Very High | Critical | Security audits, penetration testing, encryption implementation, access controls, security training | Kevin Zhang, Security Analyst | Low | High | Severe | Inherent Risk Matrix (before Controls)
7 | Performance Issues at Scale | Caused by: Inadequate load testing, infrastructure limitations, code inefficiencies Consequences: Slow response times, user complaints, system crashes | Robert Taylor, QA Lead | Medium | High | Severe | Load testing before go-live, scalable cloud infrastructure, performance monitoring, optimization sprints | Chris Brown, DevOps Engineer | Low | Medium | Moderate | Impact: |  | Very Low | Low | Medium | High | Very High
8 | Vendor/Third-Party Dependency | Caused by: Vendor instability, licensing changes, support limitations Consequences: Unexpected costs, feature limitations, forced migration | David Kumar, Solutions Architect | Low | High | Severe | Evaluate vendor stability, negotiate SLAs, maintain exit strategy, use open standards where possible | Sarah Johnson, Project Manager | Very Low | Medium | Sustainable | Probability | Very High |  |  |  | 1
9 | Budget Overrun | Caused by: Scope changes, unforeseen complexity, resource costs Consequences: Project suspension, feature cuts, stakeholder dissatisfaction | Sarah Johnson, Project Manager | Medium | High | Severe | Regular budget reviews, contingency reserves, value engineering, transparent reporting | Sarah Johnson, Project Manager | Low | Medium | Moderate |  | High |  |  |  | 1 | 2
10 | Go-Live Deployment Failure | Caused by: Inadequate testing, environment differences, timing issues Consequences: Business disruption, data corruption, rollback required | Chris Brown, DevOps Engineer | Medium | Very High | Critical | Deployment rehearsals, rollback procedures, off-hours deployment, monitoring alerts, support team standby | Chris Brown, DevOps Engineer | Low | High | Severe |  | Medium |  |  |  | 3 | 2
[13 empty] | Low |  |  |  | 1
What is a Risk Assessment? | [12 empty] | Very Low
A Risk Assessment is a systematic process used to identify, analyze, and evaluate potential risks that could negatively impact a project, organization, or process.
• Inherent Risk: The level of risk before any controls or mitigation measures are applied. Calculated using Probability × Impact. | [11 empty] | Residual Risk Matrix (after Controls)
• Residual Risk: The level of risk remaining after controls and mitigation measures have been implemented. | [11 empty] | Impact: |  | Very Low | Low | Medium | High | Very High
• Risk Matrix: A visual tool that maps Probability (likelihood) against Impact (severity) to determine overall risk ratings (Sustainable, Moderate, Severe, Critical). | [11 empty] | Probability | Very High
Benefits: Helps prioritize risks, allocate resources effectively, implement appropriate controls, and ensure stakeholders are informed of potential threats to project success. | [12 empty] | High
[13 empty] | Medium |  |  | 2 | 1
[13 empty] | Low |  |  | 4 | 2
[13 empty] | Very Low |  |  | 1

## Requirement Traceability
Requirement Traceability Matrix
| Project Name: | Enterprise CRM System Implementation |  |  | Document Author: | Michael Chen
Req# Unique ID | Requirement Name / Description | Requested / Approved By | Scope Deliverable or Feature | Scope # Unique ID | User Story or Work Package | Assigned To | Test Case | Current Status
REQ-001 | User Authentication & Single Sign-On | Tom Williams (Product Owner) | User Management Module | SCO-001 | US-101: As a user, I want to login using SSO so I can access the system securely | Kevin Zhang | TC-001: Verify SSO login with valid credentials | Complete
REQ-002 | Customer Profile Management | Tom Williams (Product Owner) | Customer Data Module | SCO-002 | US-102: As a sales rep, I want to view/edit customer profiles | Lisa Park | TC-002: Verify CRUD operations on customer profiles | Testing
REQ-003 | Lead Capture & Qualification | Sarah Johnson (PM) | Sales Pipeline Module | SCO-003 | US-103: As a sales rep, I want to capture leads from web forms | James Rodriguez | TC-003: Verify lead capture from multiple sources | Development
REQ-004 | Opportunity Pipeline Tracking | Tom Williams (Product Owner) | Sales Pipeline Module | SCO-003 | US-104: As a sales manager, I want to track deal stages | James Rodriguez | TC-004: Verify pipeline stage transitions | Development | Statuses
REQ-005 | Email Integration (Outlook/Gmail) | Michael Chen (BA) | Integration Module | SCO-004 | US-105: As a user, I want to sync emails with customer records | David Kumar | TC-005: Verify email sync functionality | Elaboration | Not Started
REQ-006 | Sales Dashboard & Reports | Sarah Johnson (PM) | Reporting Module | SCO-005 | US-106: As a manager, I want real-time sales dashboards | Lisa Park | TC-006: Verify dashboard data accuracy | Elaboration | Elaboration
REQ-007 | Mobile App Access | Tom Williams (Product Owner) | Mobile Module | SCO-006 | US-107: As a field rep, I want to access CRM on mobile | Lisa Park | TC-007: Verify mobile responsiveness | Not Started | Development
REQ-008 | Data Migration from Legacy CRM | Sarah Johnson (PM) | Data Migration | SCO-007 | US-108: As an admin, I want all historical data migrated | Emma Wilson | TC-008: Verify data integrity post-migration | Development | Testing
REQ-009 | Role-Based Access Control | Kevin Zhang (Security) | Security Module | SCO-008 | US-109: As an admin, I want to define user roles/permissions | Kevin Zhang | TC-009: Verify access restrictions by role | Testing | Complete
REQ-010 | Automated Workflow & Notifications | Michael Chen (BA) | Automation Module | SCO-009 | US-110: As a user, I want automated task reminders | James Rodriguez | TC-010: Verify workflow triggers and notifications | Not Started | Released
What is a Requirement Traceability Matrix (RTM)?
A Requirement Traceability Matrix (RTM) is a document that links requirements throughout the project lifecycle, ensuring all requirements are tested and delivered. • Req# (Unique ID): A unique identifier for each requirement to enable tracking and reference throughout the project. • Requirement Description: A clear statement of what the system must do or deliver to meet stakeholder needs. • Requested/Approved By: The stakeholder who requested the requirement and has authority to approve changes. • Scope Deliverable: The project feature or component that fulfills the requirement. • User Story: Agile format - 'As a [user], I want [goal] so that [benefit]' - describes functionality from user perspective. • Test Case: The test scenario used to verify the requirement has been correctly implemented. Benefits: Ensures complete test coverage, prevents scope creep, enables impact analysis, supports change management, and provides audit trail.

## Pareto Principle
Pareto Principle
|  |  | Pareto Line: | 70% |  | Process or Chart Name: | Enterprise CRM System Implementation
| Options | Data | % | Cumulative | Line
| Data Migration Errors | 45 | 33.09% | 33.09% | 0.7
| UI/UX Bugs | 30 | 22.06% | 55.15% | 0.7
| API Integration Failures | 20 | 14.71% | 69.85% | 0.7
| Performance Issues | 15 | 11.03% | 80.88% | 0.7
| Security Vulnerabilities | 10 | 7.353% | 88.24% | 0.7
| Authentication Errors | 5 | 3.676% | 91.91% | 0.7
| Report Generation Issues | 4 | 2.941% | 94.85% | 0.7
| Mobile App Crashes | 3 | 2.206% | 97.06% | 0.7
| Notification Failures | 2 | 1.471% | 98.53% | 0.7
| Search Functionality Bugs | 2 | 1.471% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
|  |  | 0% | 100% | 0.7
| TOTAL | 136 | 100%
What is the Pareto Principle?
The Pareto Principle (80/20 Rule) states that roughly 80% of effects come from 20% of causes. In business, this means focusing on the vital few factors that drive most results. • 80/20 Rule: Approximately 80% of outcomes result from 20% of inputs. Identify and prioritize the critical few over the trivial many. • Options/Categories: The items being analyzed (e.g., defect types, issues, causes). Sorted from highest to lowest impact. • Data/Frequency: The count or value for each option. Higher values indicate greater impact or occurrence. • Cumulative %: Running total percentage showing how much of the total each option contributes when combined with previous items. • Pareto Line (70-80%): The threshold line indicating where the vital few end. Items below this line are the 'critical few' to focus on.

## Heatmap
Project Management Heatmap - Enterprise CRM System Implementation
Activity Status Overview by Key Metrics
Activity | % Complete | Schedule | Risk Level | Resource Load | Quality | Budget | Overall Health
Project Initiation & Planning | 100% | 5 | 5 | 4 | 5 | 5 | 5
Requirements Gathering & Analysis | 100% | 5 | 4 | 4 | 5 | 5 | 5
System Architecture Design | 100% | 5 | 4 | 4 | 4 | 5 | 4
Database Design & Development | 20% | 1 | 2 | 3 | 2 | 3 | 2
Backend API Development | 40% | 3 | 3 | 4 | 3 | 4 | 3
Frontend UI Development | 30% | 3 | 3 | 4 | 3 | 3 | 3
Integration & System Testing | 0% | 4 | 3 | 3 | 3 | 4 | 3
User Acceptance Testing (UAT) | 0% | 4 | 3 | 3 | 3 | 4 | 3
Deployment & Go-Live | 0% | 4 | 2 | 3 | 3 | 4 | 3
Post Go-Live Support & Training | 0% | 4 | 3 | 3 | 3 | 4 | 3
Legend (1-5 Scale) |  |  |  | Project Health Summary
5 - Excellent | Green | On track / No issues |  | Total Activities: | 10 | Avg Overall Health: | 3.4
4 - Good | Light Green | Minor concerns |  | Completed (100%): | 3 | Critical Items (1-2): | 5
3 - Fair | Yellow | Needs attention |  | In Progress: | 3 | Fair Items (3): | 26
2 - Poor | Orange | At risk |  | Not Started: | 4 | Good/Excellent (4-5): | 29
1 - Critical | Red | Immediate action required |  | Avg Completion: | 39%
What is a Project Heatmap?
A Project Heatmap is a visual management tool that uses color-coding to quickly communicate the health status of project activities across multiple dimensions. • Schedule: How well is the activity tracking against planned timeline? • Risk Level: Current risk exposure for the activity (linked to Risk Assessment) • Resource Load: Are resources adequately allocated and available? • Quality: Are deliverables meeting quality standards? • Budget: Is spending within planned budget? • Overall Health: Aggregate score indicating overall activity status Benefits: Enables quick identification of problem areas, facilitates stakeholder communication, supports proactive decision-making, and provides at-a-glance project status.