## 🎯 QA Dashboard
🐞 SOFTWARE QUALITY ASSURANCE DASHBOARD
Project: Phoenix Platform
Sprint 8 (Current) ¦ Total Bugs: 201 ¦ Open: 57 ¦ Critical Open: 2 ¦ Report Date: May 23, 2026
🐛 |  | 🔴 | ✅ |  |  |  | 💀 |  |  | ⏱️ |  |  | 🎯
201 |  | 57 | 79.6% |  |  |  | 2 |  |  | 129 |  |  | 71.6%
TOTAL BUGS |  | OPEN BUGS (Status: Open, In Progress, Reopened) | PASS RATE |  |  |  | CRITICAL (Status: Open, In Progress, Reopened) |  |  | AVG DAYS OPEN |  |  | DRE
All Sprints |  | Need Attention | All Sprints |  |  |  | P0 Issues |  |  | Days per Bug |  |  | Defect Removal
📊 BUG SEVERITY DISTRIBUTION |  |  |  |  | 📊 BUG STATUS OVERVIEW
📈 BUGS BY MODULE |  |  |  |  | 📈 SPRINT TEST EXECUTION
📉 MONTHLY BUG TREND |  |  |  |  | 📉 DEFECT REMOVAL EFFICIENCY
📊 BUGS BY TEST TYPE |  |  |  |  | 📊 BUGS BY ENVIRONMENT
🚨 TOP OPEN / CRITICAL BUGS — Immediate Action Required
Bug ID | Title |  |  | Severity |  | Status |  | Module | Tester |  | Sprint | Days Open
BUG-0033 | [User Mgmt] 500 error |  |  | High |  | Open |  | Search | Emma Johnson |  | Sprint 7 | 234
BUG-0002 | [Export] Memory leak |  |  | Critical |  | In Progress |  | Export | Bob Martinez |  | Sprint 7 | 226
BUG-0022 | [Dashboard] Missing validation |  |  | High |  | In Progress |  | Export | Alice Chen |  | Sprint 1 | 188
BUG-0048 | [Export] Missing validation |  |  | High |  | Reopened |  | Export | Bob Martinez |  | Sprint 2 | 178
BUG-0151 | [Admin Panel] Broken link |  |  | High |  | Open |  | Dashboard | Grace Patel |  | Sprint 5 | 169
BUG-0069 | [Payment] Crash on load |  |  | High |  | In Progress |  | Export | Grace Patel |  | Sprint 3 | 165
BUG-0025 | [Export] NullPointerException |  |  | High |  | Open |  | Reports | Alice Chen |  | Sprint 1 | 159
BUG-0200 | [Export] Broken link |  |  | High |  | Reopened |  | API Gateway | Grace Patel |  | Sprint 8 | 149
BUG-0058 | [Login] NullPointerException |  |  | High |  | Open |  | Payment | Grace Patel |  | Sprint 1 | 145
BUG-0007 | [Dashboard] Memory leak |  |  | High |  | In Progress |  | API Gateway | Emma Johnson |  | Sprint 4 | 144

## Bug Tracker
Bug ID | Title | Severity | Status | Module | Assigned Tester | Sprint | Created | Resolved | Days Open | Test Type | Environment
BUG-0001 | [Payment] 500 error | High | Closed | Dashboard | Frank Liu | Sprint 2 | 13-Mar-2026 | 17-Mar-2026 | 4 | UAT | Pre-Prod
BUG-0002 | [Export] Memory leak | Critical | In Progress | Export | Bob Martinez | Sprint 7 | 09-Oct-2025 | — | 226 | Integration | Pre-Prod
BUG-0003 | [API Gateway] Wrong calculation | High | Closed | User Mgmt | Bob Martinez | Sprint 4 | 28-Feb-2026 | 13-Mar-2026 | 13 | Regression | Dev
BUG-0004 | [Admin Panel] Timeout | Medium | Fixed | Login | Frank Liu | Sprint 8 | 24-Oct-2025 | 30-Oct-2025 | 6 | UAT | Dev
BUG-0005 | [Admin Panel] Crash on load | Critical | Fixed | Payment | Frank Liu | Sprint 2 | 05-Jan-2026 | 16-Jan-2026 | 11 | Unit | QA
BUG-0006 | [Payment] UI misalignment | High | Open | User Mgmt | David Kim | Sprint 6 | 16-Apr-2026 | — | 37 | Integration | Staging
BUG-0007 | [Dashboard] Memory leak | High | In Progress | API Gateway | Emma Johnson | Sprint 4 | 30-Dec-2025 | — | 144 | Integration | Pre-Prod
BUG-0008 | [Export] Data mismatch | High | Closed | Reports | Grace Patel | Sprint 1 | 06-Jan-2026 | 18-Jan-2026 | 12 | Integration | Dev
BUG-0009 | [Admin Panel] Crash on load | Medium | Open | Search | David Kim | Sprint 8 | 20-Dec-2025 | — | 154 | Integration | Staging
BUG-0010 | [Admin Panel] Wrong calculation | High | Verified | Notifications | Carol Singh | Sprint 4 | 05-Nov-2025 | 10-Nov-2025 | 5 | Integration | Pre-Prod
BUG-0011 | [API Gateway] Wrong calculation | Low | Closed | Dashboard | David Kim | Sprint 7 | 24-Oct-2025 | 27-Oct-2025 | 3 | UAT | Pre-Prod
BUG-0012 | [Dashboard] Broken link | High | Verified | User Mgmt | Grace Patel | Sprint 6 | 13-Feb-2026 | 14-Feb-2026 | 1 | Unit | Staging
BUG-0013 | [User Mgmt] Broken link | High | Open | API Gateway | Emma Johnson | Sprint 2 | 20-Jan-2026 | — | 123 | Performance | Staging
BUG-0014 | [Reports] 500 error | Medium | In Progress | Export | Alice Chen | Sprint 6 | 13-Mar-2026 | — | 71 | Smoke | Dev
BUG-0015 | [User Mgmt] Data mismatch | Low | Closed | Payment | Emma Johnson | Sprint 2 | 29-Oct-2025 | 12-Nov-2025 | 14 | Unit | Pre-Prod
BUG-0016 | [API Gateway] Missing validation | Low | Verified | API Gateway | Carol Singh | Sprint 7 | 18-Oct-2025 | 21-Oct-2025 | 3 | Integration | QA
BUG-0017 | [Reports] Missing validation | High | Reopened | Search | Alice Chen | Sprint 4 | 01-Apr-2026 | — | 52 | Integration | Dev
BUG-0018 | [Payment] NullPointerException | Critical | Verified | Login | Bob Martinez | Sprint 2 | 26-Dec-2025 | 05-Jan-2026 | 10 | Unit | Staging
BUG-0019 | [Payment] Broken link | Medium | Fixed | Admin Panel | Emma Johnson | Sprint 8 | 19-Oct-2025 | 27-Oct-2025 | 8 | Integration | Pre-Prod
BUG-0020 | [Notifications] Crash on load | High | Open | Notifications | David Kim | Sprint 1 | 13-Jan-2026 | — | 130 | Performance | Dev
BUG-0021 | [Dashboard] Data mismatch | Medium | Fixed | Payment | Emma Johnson | Sprint 8 | 16-Oct-2025 | 30-Oct-2025 | 14 | Integration | Pre-Prod
BUG-0022 | [Dashboard] Missing validation | High | In Progress | Export | Alice Chen | Sprint 1 | 16-Nov-2025 | — | 188 | Performance | Dev
BUG-0023 | [Notifications] Missing validation | Low | Closed | Payment | Grace Patel | Sprint 7 | 24-Oct-2025 | 27-Oct-2025 | 3 | Unit | QA
BUG-0024 | [Search] Timeout | Critical | Fixed | Export | Frank Liu | Sprint 8 | 06-Jan-2026 | 19-Jan-2026 | 13 | Integration | QA
BUG-0025 | [Export] NullPointerException | High | Open | Reports | Alice Chen | Sprint 1 | 15-Dec-2025 | — | 159 | UAT | Pre-Prod
BUG-0026 | [Export] UI misalignment | Low | Verified | API Gateway | Alice Chen | Sprint 2 | 06-Feb-2026 | 07-Feb-2026 | 1 | Performance | QA
BUG-0027 | [Admin Panel] Memory leak | High | Closed | Admin Panel | Alice Chen | Sprint 7 | 12-Jan-2026 | 16-Jan-2026 | 4 | Performance | Staging
BUG-0028 | [User Mgmt] Wrong calculation | High | Verified | User Mgmt | David Kim | Sprint 6 | 06-Dec-2025 | 10-Dec-2025 | 4 | Unit | Dev
BUG-0029 | [Dashboard] Broken link | Medium | Verified | Export | Carol Singh | Sprint 3 | 26-Jan-2026 | 28-Jan-2026 | 2 | Regression | Dev
BUG-0030 | [Export] Timeout | Medium | In Progress | Export | Alice Chen | Sprint 5 | 02-Dec-2025 | — | 172 | Performance | Dev
BUG-0031 | [Export] 500 error | High | Closed | User Mgmt | Emma Johnson | Sprint 4 | 04-Nov-2025 | 16-Nov-2025 | 12 | Performance | Staging
BUG-0032 | [Search] Timeout | Medium | Closed | Login | Alice Chen | Sprint 7 | 22-Nov-2025 | 01-Dec-2025 | 9 | Regression | Dev
BUG-0033 | [User Mgmt] 500 error | High | Open | Search | Emma Johnson | Sprint 7 | 01-Oct-2025 | — | 234 | UAT | Dev
BUG-0034 | [Export] NullPointerException | Critical | Closed | Reports | Emma Johnson | Sprint 3 | 29-Oct-2025 | 01-Nov-2025 | 3 | Smoke | QA
BUG-0035 | [Login] Crash on load | High | Closed | Payment | Frank Liu | Sprint 2 | 11-Oct-2025 | 24-Oct-2025 | 13 | Regression | Pre-Prod
BUG-0036 | [API Gateway] 500 error | Medium | Closed | Login | Bob Martinez | Sprint 6 | 08-Mar-2026 | 12-Mar-2026 | 4 | Smoke | QA
BUG-0037 | [Login] Missing validation | High | Verified | Payment | Grace Patel | Sprint 8 | 08-Dec-2025 | 15-Dec-2025 | 7 | Regression | Staging
BUG-0038 | [Reports] Timeout | High | Verified | Dashboard | Grace Patel | Sprint 5 | 28-Nov-2025 | 05-Dec-2025 | 7 | Regression | Pre-Prod
BUG-0039 | [Dashboard] Timeout | Low | Verified | Admin Panel | Carol Singh | Sprint 1 | 23-Mar-2026 | 24-Mar-2026 | 1 | Unit | Pre-Prod
BUG-0040 | [Export] UI misalignment | Medium | Fixed | Admin Panel | Bob Martinez | Sprint 5 | 28-Dec-2025 | 07-Jan-2026 | 10 | Unit | Pre-Prod
BUG-0041 | [Payment] Crash on load | Medium | Closed | Dashboard | Frank Liu | Sprint 6 | 01-Oct-2025 | 12-Oct-2025 | 11 | UAT | Staging
BUG-0042 | [Export] Timeout | Low | Verified | Notifications | Carol Singh | Sprint 7 | 19-Mar-2026 | 24-Mar-2026 | 5 | Performance | Staging
BUG-0043 | [API Gateway] Memory leak | High | Fixed | User Mgmt | David Kim | Sprint 1 | 19-Feb-2026 | 26-Feb-2026 | 7 | Regression | Staging
BUG-0044 | [Reports] Missing validation | Medium | Verified | Search | Frank Liu | Sprint 4 | 23-Nov-2025 | 04-Dec-2025 | 11 | UAT | Pre-Prod
BUG-0045 | [Export] Memory leak | High | Open | Dashboard | Grace Patel | Sprint 4 | 07-Apr-2026 | — | 46 | Performance | Staging
BUG-0046 | [Login] Data mismatch | Low | Open | Admin Panel | Grace Patel | Sprint 2 | 27-Nov-2025 | — | 177 | Smoke | Pre-Prod
BUG-0047 | [Search] Wrong calculation | Medium | Verified | API Gateway | Frank Liu | Sprint 1 | 11-Mar-2026 | 18-Mar-2026 | 7 | Unit | Pre-Prod
BUG-0048 | [Export] Missing validation | High | Reopened | Export | Bob Martinez | Sprint 2 | 26-Nov-2025 | — | 178 | Smoke | QA
BUG-0049 | [Admin Panel] Crash on load | Medium | Reopened | Search | Emma Johnson | Sprint 7 | 27-Jan-2026 | — | 116 | UAT | Pre-Prod
BUG-0050 | [Payment] Timeout | Medium | Fixed | Export | David Kim | Sprint 4 | 10-Nov-2025 | 15-Nov-2025 | 5 | Regression | Pre-Prod
BUG-0051 | [Reports] Crash on load | Medium | In Progress | Dashboard | Bob Martinez | Sprint 3 | 20-Oct-2025 | — | 215 | Integration | Pre-Prod
BUG-0052 | [Notifications] Wrong calculation | High | In Progress | Export | David Kim | Sprint 7 | 27-Mar-2026 | — | 57 | Unit | QA
BUG-0053 | [Login] Memory leak | Medium | Closed | Search | Alice Chen | Sprint 6 | 16-Jan-2026 | 28-Jan-2026 | 12 | Regression | Pre-Prod
BUG-0054 | [Admin Panel] Data mismatch | Medium | Closed | Payment | Carol Singh | Sprint 7 | 16-Jan-2026 | 29-Jan-2026 | 13 | Smoke | Dev
BUG-0055 | [API Gateway] Missing validation | High | Verified | Admin Panel | Emma Johnson | Sprint 1 | 08-Jan-2026 | 15-Jan-2026 | 7 | Smoke | Dev
BUG-0056 | [Search] 500 error | Medium | Open | User Mgmt | David Kim | Sprint 6 | 22-Oct-2025 | — | 213 | Integration | Pre-Prod
BUG-0057 | [Notifications] Timeout | High | Closed | Dashboard | David Kim | Sprint 1 | 23-Dec-2025 | 28-Dec-2025 | 5 | Performance | Dev
BUG-0058 | [Login] NullPointerException | High | Open | Payment | Grace Patel | Sprint 1 | 29-Dec-2025 | — | 145 | UAT | QA
BUG-0059 | [Payment] Missing validation | High | Verified | User Mgmt | Grace Patel | Sprint 6 | 01-Dec-2025 | 11-Dec-2025 | 10 | Integration | Dev
BUG-0060 | [Dashboard] Memory leak | Low | Reopened | User Mgmt | Emma Johnson | Sprint 7 | 18-Apr-2026 | — | 35 | Smoke | QA
BUG-0061 | [Dashboard] Timeout | Medium | Closed | Admin Panel | Grace Patel | Sprint 2 | 20-Oct-2025 | 24-Oct-2025 | 4 | UAT | Dev
BUG-0062 | [Export] Crash on load | Medium | Verified | Notifications | Grace Patel | Sprint 8 | 28-Dec-2025 | 30-Dec-2025 | 2 | Unit | Pre-Prod
BUG-0063 | [API Gateway] Wrong calculation | Medium | Closed | Export | Frank Liu | Sprint 5 | 01-Jan-2026 | 13-Jan-2026 | 12 | UAT | Pre-Prod
BUG-0064 | [Reports] Data mismatch | Medium | Closed | Dashboard | Carol Singh | Sprint 8 | 28-Jan-2026 | 02-Feb-2026 | 5 | Integration | Pre-Prod
BUG-0065 | [Search] Crash on load | Medium | Fixed | Search | Bob Martinez | Sprint 6 | 23-Feb-2026 | 24-Feb-2026 | 1 | Regression | Staging
BUG-0066 | [Export] NullPointerException | Low | Verified | Payment | Alice Chen | Sprint 4 | 11-Dec-2025 | 16-Dec-2025 | 5 | Performance | Pre-Prod
BUG-0067 | [Search] Missing validation | Medium | In Progress | Login | Alice Chen | Sprint 5 | 03-Feb-2026 | — | 109 | Integration | Pre-Prod
BUG-0068 | [Search] Broken link | High | Verified | Reports | David Kim | Sprint 6 | 27-Mar-2026 | 02-Apr-2026 | 6 | Regression | Pre-Prod
BUG-0069 | [Payment] Crash on load | High | In Progress | Export | Grace Patel | Sprint 3 | 09-Dec-2025 | — | 165 | Integration | QA
BUG-0070 | [Export] Memory leak | Medium | Closed | Dashboard | Grace Patel | Sprint 4 | 08-Apr-2026 | 21-Apr-2026 | 13 | Regression | QA
BUG-0071 | [Export] 500 error | High | Open | Login | Alice Chen | Sprint 5 | 01-Jan-2026 | — | 142 | Performance | QA
BUG-0072 | [Login] Memory leak | Low | Fixed | Search | David Kim | Sprint 8 | 13-Mar-2026 | 27-Mar-2026 | 14 | Regression | QA
BUG-0073 | [Dashboard] Wrong calculation | High | Closed | Dashboard | Emma Johnson | Sprint 1 | 14-Oct-2025 | 16-Oct-2025 | 2 | Integration | QA
BUG-0074 | [Payment] UI misalignment | Low | Open | Notifications | Emma Johnson | Sprint 4 | 22-Feb-2026 | — | 90 | UAT | Pre-Prod
BUG-0075 | [Notifications] Timeout | Low | Fixed | Admin Panel | Alice Chen | Sprint 2 | 24-Jan-2026 | 03-Feb-2026 | 10 | Integration | QA
BUG-0076 | [API Gateway] Broken link | Medium | In Progress | API Gateway | Alice Chen | Sprint 7 | 07-Dec-2025 | — | 167 | Smoke | Pre-Prod
BUG-0077 | [Search] UI misalignment | Critical | Fixed | Payment | Carol Singh | Sprint 4 | 14-Dec-2025 | 19-Dec-2025 | 5 | Smoke | Dev
BUG-0078 | [User Mgmt] 500 error | High | Open | Login | Bob Martinez | Sprint 5 | 17-Feb-2026 | — | 95 | UAT | Staging
BUG-0079 | [Notifications] Timeout | High | Verified | Export | David Kim | Sprint 8 | 21-Jan-2026 | 02-Feb-2026 | 12 | Unit | Dev
BUG-0080 | [Dashboard] Data mismatch | Medium | Verified | Admin Panel | Emma Johnson | Sprint 1 | 19-Jan-2026 | 20-Jan-2026 | 1 | Performance | Staging
BUG-0081 | [Export] Missing validation | Critical | Closed | API Gateway | Emma Johnson | Sprint 7 | 25-Feb-2026 | 05-Mar-2026 | 8 | Performance | Pre-Prod
BUG-0082 | [Dashboard] 500 error | Medium | Fixed | Notifications | Frank Liu | Sprint 8 | 24-Oct-2025 | 30-Oct-2025 | 6 | Regression | Pre-Prod
BUG-0083 | [User Mgmt] Crash on load | Medium | Fixed | Notifications | Grace Patel | Sprint 1 | 13-Apr-2026 | 19-Apr-2026 | 6 | Performance | Pre-Prod
BUG-0084 | [Search] Missing validation | Critical | Fixed | Login | Bob Martinez | Sprint 5 | 14-Jan-2026 | 24-Jan-2026 | 10 | UAT | QA
BUG-0085 | [Login] Memory leak | Medium | Verified | Payment | Frank Liu | Sprint 3 | 13-Dec-2025 | 15-Dec-2025 | 2 | Regression | Dev
BUG-0086 | [Dashboard] Missing validation | Medium | In Progress | API Gateway | David Kim | Sprint 5 | 19-Feb-2026 | — | 93 | UAT | Staging
BUG-0087 | [Payment] Missing validation | Low | Reopened | API Gateway | David Kim | Sprint 4 | 15-Jan-2026 | — | 128 | UAT | QA
BUG-0088 | [Reports] Broken link | High | Closed | Login | Carol Singh | Sprint 5 | 18-Oct-2025 | 25-Oct-2025 | 7 | UAT | Pre-Prod
BUG-0089 | [Export] Broken link | Medium | Fixed | Search | Carol Singh | Sprint 4 | 08-Nov-2025 | 14-Nov-2025 | 6 | Performance | QA
BUG-0090 | [Login] Crash on load | Medium | Closed | Search | Frank Liu | Sprint 7 | 24-Feb-2026 | 03-Mar-2026 | 7 | Smoke | QA
BUG-0091 | [Admin Panel] Crash on load | Low | Open | Dashboard | Grace Patel | Sprint 8 | 04-Feb-2026 | — | 108 | Unit | Pre-Prod
BUG-0092 | [API Gateway] UI misalignment | Medium | Fixed | User Mgmt | Carol Singh | Sprint 7 | 04-Oct-2025 | 15-Oct-2025 | 11 | Performance | Dev
BUG-0093 | [Reports] Missing validation | Low | Closed | Export | Alice Chen | Sprint 2 | 24-Dec-2025 | 31-Dec-2025 | 7 | Integration | Staging
BUG-0094 | [Dashboard] Missing validation | Medium | Fixed | User Mgmt | Alice Chen | Sprint 1 | 28-Nov-2025 | 30-Nov-2025 | 2 | Regression | Dev
BUG-0095 | [Export] Wrong calculation | Medium | Fixed | API Gateway | Bob Martinez | Sprint 3 | 15-Dec-2025 | 19-Dec-2025 | 4 | Unit | Pre-Prod
BUG-0096 | [API Gateway] Data mismatch | Medium | Fixed | User Mgmt | David Kim | Sprint 5 | 08-Mar-2026 | 18-Mar-2026 | 10 | Performance | Dev
BUG-0097 | [Dashboard] Missing validation | Low | Verified | Admin Panel | Carol Singh | Sprint 7 | 28-Jan-2026 | 31-Jan-2026 | 3 | Performance | Staging
BUG-0098 | [Notifications] Missing validation | Low | In Progress | Payment | David Kim | Sprint 6 | 25-Jan-2026 | — | 118 | UAT | Staging
BUG-0099 | [Notifications] Timeout | High | Reopened | Admin Panel | Grace Patel | Sprint 1 | 29-Mar-2026 | — | 55 | UAT | Pre-Prod
BUG-0100 | [Reports] Data mismatch | Low | In Progress | Payment | Emma Johnson | Sprint 5 | 13-Dec-2025 | — | 161 | Performance | QA
BUG-0101 | [User Mgmt] Missing validation | Critical | Verified | Admin Panel | Carol Singh | Sprint 3 | 10-Mar-2026 | 11-Mar-2026 | 1 | Unit | Staging
BUG-0102 | [API Gateway] Broken link | Medium | In Progress | Reports | Emma Johnson | Sprint 5 | 23-Dec-2025 | — | 151 | Integration | Staging
BUG-0103 | [Reports] UI misalignment | Low | Fixed | Dashboard | Bob Martinez | Sprint 4 | 01-Feb-2026 | 15-Feb-2026 | 14 | Performance | Pre-Prod
BUG-0104 | [User Mgmt] Broken link | Medium | Closed | Search | Carol Singh | Sprint 5 | 20-Feb-2026 | 21-Feb-2026 | 1 | UAT | Pre-Prod
BUG-0105 | [Payment] Missing validation | Low | Open | Admin Panel | Emma Johnson | Sprint 6 | 13-Mar-2026 | — | 71 | UAT | QA
BUG-0106 | [User Mgmt] Wrong calculation | Critical | Closed | API Gateway | Alice Chen | Sprint 1 | 15-Mar-2026 | 27-Mar-2026 | 12 | Regression | Pre-Prod
BUG-0107 | [Notifications] Missing validation | Critical | Closed | Export | David Kim | Sprint 3 | 30-Oct-2025 | 02-Nov-2025 | 3 | Smoke | Dev
BUG-0108 | [Login] Crash on load | Medium | Closed | Search | David Kim | Sprint 4 | 03-Feb-2026 | 08-Feb-2026 | 5 | Regression | Dev
BUG-0109 | [Reports] NullPointerException | Medium | Closed | User Mgmt | Bob Martinez | Sprint 2 | 25-Mar-2026 | 05-Apr-2026 | 11 | Smoke | Dev
BUG-0110 | [Login] Crash on load | High | Verified | API Gateway | Grace Patel | Sprint 4 | 19-Mar-2026 | 20-Mar-2026 | 1 | Unit | QA
BUG-0111 | [API Gateway] Memory leak | High | Closed | User Mgmt | Grace Patel | Sprint 3 | 28-Feb-2026 | 06-Mar-2026 | 6 | Integration | Staging
BUG-0112 | [Login] Crash on load | High | Closed | Payment | Emma Johnson | Sprint 6 | 14-Nov-2025 | 17-Nov-2025 | 3 | Unit | QA
BUG-0113 | [Dashboard] UI misalignment | Critical | Closed | Search | Grace Patel | Sprint 6 | 07-Dec-2025 | 16-Dec-2025 | 9 | UAT | Dev
BUG-0114 | [Export] Timeout | Medium | Closed | Login | Alice Chen | Sprint 8 | 24-Jan-2026 | 25-Jan-2026 | 1 | Smoke | Pre-Prod
BUG-0115 | [Dashboard] UI misalignment | High | Verified | Admin Panel | Bob Martinez | Sprint 2 | 25-Mar-2026 | 02-Apr-2026 | 8 | Integration | Staging
BUG-0116 | [Notifications] Memory leak | Medium | Verified | User Mgmt | David Kim | Sprint 7 | 09-Mar-2026 | 15-Mar-2026 | 6 | Unit | Dev
BUG-0117 | [Payment] Wrong calculation | Medium | Closed | Payment | David Kim | Sprint 6 | 17-Mar-2026 | 29-Mar-2026 | 12 | Smoke | Pre-Prod
BUG-0118 | [User Mgmt] Crash on load | Medium | Fixed | Search | Alice Chen | Sprint 2 | 15-Jan-2026 | 21-Jan-2026 | 6 | Unit | Dev
BUG-0119 | [API Gateway] Broken link | Critical | Closed | Admin Panel | Emma Johnson | Sprint 6 | 19-Jan-2026 | 01-Feb-2026 | 13 | Performance | Dev
BUG-0120 | [Notifications] NullPointerException | Medium | Verified | Admin Panel | Carol Singh | Sprint 6 | 14-Jan-2026 | 27-Jan-2026 | 13 | Unit | QA
BUG-0121 | [Dashboard] Crash on load | Medium | In Progress | Export | Carol Singh | Sprint 2 | 09-Nov-2025 | — | 195 | Regression | QA
BUG-0122 | [Admin Panel] Memory leak | Low | Reopened | Export | Alice Chen | Sprint 5 | 18-Jan-2026 | — | 125 | Unit | QA
BUG-0123 | [Reports] NullPointerException | Medium | Fixed | API Gateway | Emma Johnson | Sprint 7 | 09-Dec-2025 | 15-Dec-2025 | 6 | Unit | QA
BUG-0124 | [Export] Data mismatch | Medium | Open | Notifications | David Kim | Sprint 6 | 08-Apr-2026 | — | 45 | Integration | Staging
BUG-0125 | [Admin Panel] UI misalignment | Medium | Closed | API Gateway | Bob Martinez | Sprint 1 | 19-Dec-2025 | 29-Dec-2025 | 10 | Performance | Dev
BUG-0126 | [Search] Wrong calculation | Medium | Fixed | Payment | Grace Patel | Sprint 2 | 09-Dec-2025 | 19-Dec-2025 | 10 | Regression | Pre-Prod
BUG-0127 | [Export] Timeout | High | Verified | Payment | David Kim | Sprint 1 | 29-Oct-2025 | 06-Nov-2025 | 8 | Unit | QA
BUG-0128 | [User Mgmt] Timeout | Low | Closed | Dashboard | Alice Chen | Sprint 8 | 17-Dec-2025 | 30-Dec-2025 | 13 | Performance | Pre-Prod
BUG-0129 | [Export] Broken link | High | Verified | Reports | Alice Chen | Sprint 7 | 14-Nov-2025 | 18-Nov-2025 | 4 | Performance | Dev
BUG-0130 | [Reports] Memory leak | Critical | Closed | Admin Panel | David Kim | Sprint 7 | 20-Jan-2026 | 03-Feb-2026 | 14 | Regression | Dev
BUG-0131 | [Admin Panel] Missing validation | Critical | Fixed | Reports | Alice Chen | Sprint 7 | 12-Jan-2026 | 25-Jan-2026 | 13 | Unit | QA
BUG-0132 | [User Mgmt] Crash on load | Medium | Verified | Reports | Grace Patel | Sprint 3 | 20-Jan-2026 | 27-Jan-2026 | 7 | Unit | Dev
BUG-0133 | [Reports] 500 error | Medium | Closed | Dashboard | Bob Martinez | Sprint 5 | 13-Feb-2026 | 19-Feb-2026 | 6 | Integration | QA
BUG-0134 | [API Gateway] Missing validation | High | Closed | Admin Panel | Grace Patel | Sprint 8 | 04-Mar-2026 | 06-Mar-2026 | 2 | Performance | Staging
BUG-0135 | [Search] Timeout | High | Fixed | User Mgmt | Emma Johnson | Sprint 1 | 10-Mar-2026 | 18-Mar-2026 | 8 | Regression | Dev
BUG-0136 | [Reports] Timeout | Medium | Open | Dashboard | Emma Johnson | Sprint 7 | 19-Dec-2025 | — | 155 | Smoke | Dev
BUG-0137 | [Reports] Memory leak | Low | Verified | Export | Bob Martinez | Sprint 1 | 24-Jan-2026 | 28-Jan-2026 | 4 | Smoke | Dev
BUG-0138 | [API Gateway] NullPointerException | Low | Open | Search | David Kim | Sprint 3 | 27-Dec-2025 | — | 147 | Regression | Staging
BUG-0139 | [Admin Panel] NullPointerException | Medium | Closed | Reports | Alice Chen | Sprint 6 | 12-Dec-2025 | 23-Dec-2025 | 11 | Unit | Pre-Prod
BUG-0140 | [API Gateway] Crash on load | High | Closed | Admin Panel | Frank Liu | Sprint 3 | 12-Dec-2025 | 22-Dec-2025 | 10 | Regression | Staging
BUG-0141 | [Dashboard] Timeout | Medium | Fixed | Notifications | Frank Liu | Sprint 6 | 17-Mar-2026 | 27-Mar-2026 | 10 | Integration | Dev
BUG-0142 | [Reports] Timeout | Medium | Fixed | Payment | Carol Singh | Sprint 8 | 15-Mar-2026 | 16-Mar-2026 | 1 | Integration | QA
BUG-0143 | [Dashboard] Broken link | High | Fixed | Export | Grace Patel | Sprint 1 | 05-Nov-2025 | 18-Nov-2025 | 13 | Performance | Staging
BUG-0144 | [API Gateway] 500 error | Medium | Verified | Admin Panel | Grace Patel | Sprint 3 | 15-Apr-2026 | 18-Apr-2026 | 3 | Performance | Pre-Prod
BUG-0145 | [Search] Memory leak | Medium | Verified | Search | Bob Martinez | Sprint 4 | 12-Oct-2025 | 16-Oct-2025 | 4 | Regression | Pre-Prod
BUG-0146 | [Search] Timeout | Medium | Closed | Notifications | Emma Johnson | Sprint 7 | 19-Nov-2025 | 27-Nov-2025 | 8 | Integration | QA
BUG-0147 | [Search] Crash on load | High | In Progress | Dashboard | Frank Liu | Sprint 2 | 04-Mar-2026 | — | 80 | Regression | Dev
BUG-0148 | [API Gateway] Wrong calculation | High | Fixed | Payment | Grace Patel | Sprint 8 | 14-Apr-2026 | 23-Apr-2026 | 9 | Regression | Dev
BUG-0149 | [Notifications] UI misalignment | Critical | Fixed | Payment | Alice Chen | Sprint 6 | 15-Jan-2026 | 19-Jan-2026 | 4 | Unit | Staging
BUG-0150 | [Search] 500 error | High | Fixed | Search | David Kim | Sprint 1 | 07-Nov-2025 | 21-Nov-2025 | 14 | Unit | Dev
BUG-0151 | [Admin Panel] Broken link | High | Open | Dashboard | Grace Patel | Sprint 5 | 05-Dec-2025 | — | 169 | Integration | Staging
BUG-0152 | [Admin Panel] Missing validation | Critical | Fixed | Dashboard | Grace Patel | Sprint 8 | 01-Nov-2025 | 14-Nov-2025 | 13 | UAT | Dev
BUG-0153 | [API Gateway] Timeout | Medium | In Progress | Login | Emma Johnson | Sprint 6 | 11-Mar-2026 | — | 73 | Integration | Pre-Prod
BUG-0154 | [Reports] UI misalignment | Medium | Open | Export | Emma Johnson | Sprint 1 | 17-Nov-2025 | — | 187 | Smoke | Pre-Prod
BUG-0155 | [User Mgmt] NullPointerException | Medium | Reopened | Dashboard | Carol Singh | Sprint 4 | 12-Oct-2025 | — | 223 | Performance | Dev
BUG-0156 | [Login] Crash on load | Medium | Closed | Reports | Grace Patel | Sprint 3 | 16-Apr-2026 | 19-Apr-2026 | 3 | Performance | Pre-Prod
BUG-0157 | [API Gateway] UI misalignment | Medium | In Progress | Search | Alice Chen | Sprint 5 | 28-Mar-2026 | — | 56 | Integration | Dev
BUG-0158 | [Export] Wrong calculation | Low | Fixed | Export | David Kim | Sprint 5 | 21-Nov-2025 | 26-Nov-2025 | 5 | Unit | QA
BUG-0159 | [Reports] Timeout | Medium | Closed | Reports | David Kim | Sprint 7 | 13-Dec-2025 | 27-Dec-2025 | 14 | Performance | Pre-Prod
BUG-0160 | [Search] Crash on load | High | In Progress | Export | Carol Singh | Sprint 2 | 07-Jan-2026 | — | 136 | Performance | Pre-Prod
BUG-0161 | [API Gateway] Broken link | Medium | Reopened | Reports | Alice Chen | Sprint 2 | 21-Oct-2025 | — | 214 | Regression | Staging
BUG-0162 | [Search] Crash on load | Medium | Verified | Login | Frank Liu | Sprint 6 | 18-Dec-2025 | 21-Dec-2025 | 3 | UAT | Pre-Prod
BUG-0163 | [Dashboard] Wrong calculation | Medium | Closed | Export | Grace Patel | Sprint 3 | 10-Dec-2025 | 11-Dec-2025 | 1 | Unit | QA
BUG-0164 | [Dashboard] Data mismatch | Medium | Fixed | Reports | Carol Singh | Sprint 7 | 05-Mar-2026 | 08-Mar-2026 | 3 | UAT | Dev
BUG-0165 | [Reports] Missing validation | High | Fixed | Dashboard | Emma Johnson | Sprint 3 | 04-Mar-2026 | 10-Mar-2026 | 6 | UAT | Staging
BUG-0166 | [Login] 500 error | High | Fixed | Export | David Kim | Sprint 2 | 10-Jan-2026 | 12-Jan-2026 | 2 | Regression | Staging
BUG-0167 | [User Mgmt] Missing validation | Medium | Reopened | Dashboard | Bob Martinez | Sprint 2 | 30-Mar-2026 | — | 54 | Smoke | QA
BUG-0168 | [Reports] Crash on load | Medium | Open | Dashboard | Emma Johnson | Sprint 5 | 01-Apr-2026 | — | 52 | Regression | QA
BUG-0169 | [Reports] Broken link | Medium | Verified | Dashboard | Bob Martinez | Sprint 3 | 01-Apr-2026 | 04-Apr-2026 | 3 | Integration | Pre-Prod
BUG-0170 | [Export] 500 error | Medium | Verified | Dashboard | Alice Chen | Sprint 5 | 07-Oct-2025 | 15-Oct-2025 | 8 | Smoke | Pre-Prod
BUG-0171 | [Dashboard] 500 error | Medium | Fixed | Dashboard | David Kim | Sprint 8 | 12-Feb-2026 | 22-Feb-2026 | 10 | Performance | Staging
BUG-0172 | [Admin Panel] 500 error | Low | Closed | API Gateway | David Kim | Sprint 1 | 02-Nov-2025 | 13-Nov-2025 | 11 | Unit | QA
BUG-0173 | [Payment] Crash on load | High | Fixed | User Mgmt | Grace Patel | Sprint 2 | 17-Dec-2025 | 29-Dec-2025 | 12 | Regression | QA
BUG-0174 | [User Mgmt] Memory leak | Low | Fixed | Dashboard | Emma Johnson | Sprint 3 | 12-Mar-2026 | 23-Mar-2026 | 11 | UAT | QA
BUG-0175 | [Reports] Memory leak | Medium | Closed | Login | Alice Chen | Sprint 1 | 13-Nov-2025 | 23-Nov-2025 | 10 | Performance | Staging
BUG-0176 | [Login] Missing validation | High | Verified | Export | Carol Singh | Sprint 5 | 16-Mar-2026 | 26-Mar-2026 | 10 | Smoke | QA
BUG-0177 | [Login] 500 error | Medium | Fixed | Notifications | David Kim | Sprint 8 | 25-Mar-2026 | 06-Apr-2026 | 12 | Integration | Staging
BUG-0178 | [Reports] Wrong calculation | High | Closed | Reports | Emma Johnson | Sprint 2 | 05-Mar-2026 | 11-Mar-2026 | 6 | Regression | QA
BUG-0179 | [Dashboard] NullPointerException | High | Fixed | Notifications | Grace Patel | Sprint 7 | 28-Jan-2026 | 31-Jan-2026 | 3 | Integration | QA
BUG-0180 | [API Gateway] Missing validation | Low | Closed | Search | David Kim | Sprint 5 | 23-Dec-2025 | 27-Dec-2025 | 4 | Smoke | Dev
BUG-0181 | [Payment] Memory leak | Low | Fixed | Login | Alice Chen | Sprint 5 | 24-Oct-2025 | 28-Oct-2025 | 4 | Smoke | Pre-Prod
BUG-0182 | [API Gateway] Timeout | Medium | Closed | Reports | Grace Patel | Sprint 7 | 13-Dec-2025 | 20-Dec-2025 | 7 | Regression | Dev
BUG-0183 | [Export] Timeout | Critical | Verified | Notifications | Emma Johnson | Sprint 8 | 11-Jan-2026 | 17-Jan-2026 | 6 | UAT | Staging
BUG-0184 | [Dashboard] Wrong calculation | Medium | Open | Reports | Emma Johnson | Sprint 6 | 09-Mar-2026 | — | 75 | Integration | QA
BUG-0185 | [Login] 500 error | Medium | Fixed | Reports | Grace Patel | Sprint 8 | 04-Mar-2026 | 05-Mar-2026 | 1 | UAT | Pre-Prod
BUG-0186 | [Admin Panel] Crash on load | Medium | Fixed | Notifications | Emma Johnson | Sprint 5 | 08-Nov-2025 | 14-Nov-2025 | 6 | UAT | Staging
BUG-0187 | [Admin Panel] Timeout | Low | Verified | Login | Carol Singh | Sprint 6 | 07-Feb-2026 | 19-Feb-2026 | 12 | Performance | Dev
BUG-0188 | [Login] Memory leak | Medium | Closed | User Mgmt | Frank Liu | Sprint 4 | 15-Jan-2026 | 27-Jan-2026 | 12 | Performance | Dev
BUG-0189 | [Admin Panel] Wrong calculation | Medium | Verified | Payment | Alice Chen | Sprint 2 | 27-Feb-2026 | 11-Mar-2026 | 12 | Integration | Dev
BUG-0190 | [Payment] Wrong calculation | High | In Progress | Admin Panel | David Kim | Sprint 1 | 21-Jan-2026 | — | 122 | Performance | QA
BUG-0191 | [Search] Broken link | High | Fixed | Reports | Bob Martinez | Sprint 8 | 10-Feb-2026 | 21-Feb-2026 | 11 | UAT | Staging
BUG-0192 | [User Mgmt] Memory leak | Medium | Closed | Payment | Bob Martinez | Sprint 5 | 17-Feb-2026 | 01-Mar-2026 | 12 | UAT | Staging
BUG-0193 | [User Mgmt] Data mismatch | Low | Reopened | Search | Carol Singh | Sprint 8 | 27-Nov-2025 | — | 177 | Regression | Staging
BUG-0194 | [Notifications] Crash on load | High | Verified | API Gateway | Carol Singh | Sprint 1 | 13-Dec-2025 | 20-Dec-2025 | 7 | Regression | Dev
BUG-0195 | [Search] Data mismatch | Low | Verified | Export | Carol Singh | Sprint 5 | 28-Dec-2025 | 09-Jan-2026 | 12 | Integration | Dev
BUG-0196 | [Login] Broken link | Medium | In Progress | Payment | Alice Chen | Sprint 2 | 07-Mar-2026 | — | 77 | Smoke | Staging
BUG-0197 | [Login] Broken link | Medium | Verified | Notifications | Frank Liu | Sprint 8 | 02-Apr-2026 | 05-Apr-2026 | 3 | Smoke | QA
BUG-0198 | [Login] UI misalignment | Low | Fixed | Admin Panel | Bob Martinez | Sprint 1 | 12-Apr-2026 | 23-Apr-2026 | 11 | Integration | Pre-Prod
BUG-0199 | [Notifications] Missing validation | Low | Open | User Mgmt | Alice Chen | Sprint 1 | 15-Nov-2025 | — | 189 | Regression | Dev
BUG-0200 | [Export] Broken link | High | Reopened | API Gateway | Grace Patel | Sprint 8 | 25-Dec-2025 | — | 149 | Regression | QA
BUG-0201 | [Login] Blank page | Critical | Open | Login | Vishvambruth Javagal | Sprint 8 | 2026-05-23 | 2026-05-23 | 0 | Regression | QA
Formulas:
Days Open = IF(OR([Bug ID]="",[Created]=""),"",IF([Resolved]="—",TODAY()-[Created],[Resolved]-[Created]))

## Test Runs
Sprint | Total Tests | Passed | Failed | Blocked | Pass Rate %
Sprint 1 | 94 | 71 | 14 | 9 | 75.5
Sprint 2 | 112 | 95 | 6 | 11 | 84.8
Sprint 3 | 123 | 106 | 9 | 8 | 86.2
Sprint 4 | 104 | 75 | 19 | 10 | 72.1
Sprint 5 | 131 | 115 | 8 | 8 | 87.8
Sprint 6 | 91 | 70 | 9 | 12 | 76.9
Sprint 7 | 97 | 77 | 13 | 7 | 79.4
Sprint 8 | 80 | 59 | 9 | 12 | 73.8

## Chart Data
📊 CHART DATA - QA DASHBOARD SOURCE
🔴 Severity | Count | 📊 Status | Count | 📦 Module | Bugs | 🏃 Sprint | Passed | Failed | Blocked | Pass Rate | 📅 Month | Bugs Opened | 🎯 Sprint | DRE % | 🧪 Test Type | Count | 🌐 Environment | Count
Critical | 19 | Open | 24 | Dashboard | 26 | Sprint 1 | 71 | 14 | 9 | 75.5 | Oct 2025 | 26 | Sprint 1 | 72.4 | UAT | 32 | Pre-Prod | 57
High | 60 | In Progress | 21 | Export | 25 | Sprint 2 | 95 | 6 | 11 | 84.8 | Nov 2025 | 25 | Sprint 2 | 65.4 | Integration | 38 | Dev | 53
Medium | 87 | Fixed | 47 | Payment | 23 | Sprint 3 | 106 | 9 | 8 | 86.2 | Dec 2025 | 40 | Sprint 3 | 83.3 | Regression | 38 | QA | 49
Low | 35 | Verified | 43 | Admin Panel | 22 | Sprint 4 | 75 | 19 | 10 | 72.1 | Jan 2026 | 37 | Sprint 4 | 70 | Unit | 31 | Staging | 42
|  | Closed | 54 | Search | 20 | Sprint 5 | 115 | 8 | 8 | 87.8 | Feb 2026 | 22 | Sprint 5 | 59.3 | Performance | 37
TOTAL | 201 | Reopened | 12 | User Mgmt | 19 | Sprint 6 | 70 | 9 | 12 | 76.9 | Mar 2026 | 36 | Sprint 6 | 69.2 | Smoke | 25 | TOTAL | 201
|  |  |  | Reports | 18 | Sprint 7 | 77 | 13 | 7 | 79.4 | Apr 2026 | 14 | Sprint 7 | 75
|  | TOTAL | 201 | API Gateway | 17 | Sprint 8 | 59 | 9 | 12 | 73.8 | May 2026 | 1 | Sprint 8 | 81.5 | TOTAL | 201
|  |  |  | Login | 16
|  |  |  | Notifications | 15 | TOTAL/AVG | 668 | 87 | 77 | 79.5625 | TOTAL | 201 | AVERAGE | 72.0125
|  |  |  | TOTAL | 201

## 🏆 Tester Scorecard
🏆 QA TESTER PERFORMANCE SCORECARD
Sprint 1–8 ¦ 201 Total Bugs ¦ 7 Testers
Rank | Tester Name | Bugs Assigned | Closed/Fixed | Critical Found | Close Rate % | Performance | Tester | Bugs | Closed | Critical | Rate | Perf
1 | Frank Liu | 18 | 17 | 2 | 94.4 | 🥇 Excellent | Alice Chen | 33 | 20 | 3 | 60.6 | 🥈 Good
2 | Carol Singh | 25 | 21 | 2 | 84 | 🥇 Excellent | Bob Martinez | 23 | 18 | 3 | 78.3 | 🥇 Excellent
3 | Bob Martinez | 23 | 18 | 3 | 78.3 | 🥇 Excellent | Carol Singh | 25 | 21 | 2 | 84 | 🥇 Excellent
4 | Grace Patel | 34 | 26 | 2 | 76.5 | 🥇 Excellent | David Kim | 34 | 23 | 2 | 67.6 | 🥈 Good
5 | David Kim | 34 | 23 | 2 | 67.6 | 🥈 Good | Emma Johnson | 33 | 19 | 4 | 57.6 | 🥉 Average
6 | Alice Chen | 33 | 20 | 3 | 60.6 | 🥈 Good | Frank Liu | 18 | 17 | 2 | 94.4 | 🥇 Excellent
7 | Emma Johnson | 33 | 19 | 4 | 57.6 | 🥉 Average | Grace Patel | 34 | 26 | 2 | 76.5 | 🥇 Excellent
8 | Vishvambruth Javagal | 1 | 0 | 1 | 0 | ⚠️ Needs Improvement | Vishvambruth Javagal | 1 | 0 | 1 | 0 | ⚠️ Needs Improvement

## 📅 Sprint Health
📅 SPRINT-BY-SPRINT HEALTH TRACKER
Sprint | Total Tests | Passed | Failed | Blocked | Pass Rate | Total Bugs | Critical | High | Medium | Low | Bugs Closed | DRE % | Health
Sprint 1 | 94 | 71 | 14 | 9 | 75.5 | 29 | 1 | 16 | 7 | 5 | 21 | 72.4 | 🟡 At Risk
Sprint 2 | 112 | 95 | 6 | 11 | 84.8 | 26 | 2 | 10 | 9 | 5 | 17 | 65.4 | 🟡 At Risk
Sprint 3 | 123 | 106 | 9 | 8 | 86.2 | 18 | 3 | 4 | 9 | 2 | 15 | 83.3 | 🟢 Healthy
Sprint 4 | 104 | 75 | 19 | 10 | 72.1 | 20 | 1 | 7 | 8 | 4 | 14 | 70 | 🟡 At Risk
Sprint 5 | 131 | 115 | 8 | 8 | 87.8 | 27 | 1 | 6 | 14 | 6 | 16 | 59.3 | 🟡 At Risk
Sprint 6 | 91 | 70 | 9 | 12 | 76.9 | 26 | 3 | 6 | 14 | 3 | 18 | 69.2 | 🟡 At Risk
Sprint 7 | 97 | 77 | 13 | 7 | 79.4 | 28 | 4 | 5 | 13 | 6 | 21 | 75 | 🟡 At Risk
Sprint 8 | 80 | 59 | 9 | 12 | 73.8 | 27 | 4 | 6 | 13 | 4 | 22 | 81.5 | 🟡 At Risk