## 📋 Estimation Dashboard
📐 QA RESOURCE & BUDGET ESTIMATION DASHBOARD
Project: Phoenix Platform Modernization ¦ Release: Release 3.0 ¦ QA Lead: Jane Smith ¦ Est. Date: May 27, 2026
📌 Estimation Techniques: PERT ¦ Three-Point ¦ Story Points ¦ Analogy ¦ Use Case Points
💰 Total QA Budget | [6 empty] | 👥 QA Team Size
407680.35 | [6 empty] | 6
📅 QA Duration (Wks) | [6 empty] | 📋 Est. Test Cases
17.3 | [6 empty] | 74
📊 ESTIMATION COMPARISON BY TECHNIQUE
|  | Technique | Optimistic | Most Likely | Pessimistic | Estimate | Std Dev | Confidence
|  | PERT (Weighted) | 229 | 398 | 634 | 409.1667 | 16.38 | 377.1 – 441.3
|  | Three-Point (Triangular) | 229 | 398 | 634 | 420.3333 | 16.3 | 388.4 – 452.3
|  | Story Points (Agile) | N/A | 372.5 | N/A | 372.5 | N/A | 🟢 High
|  | Analogy-Based | N/A | 322 | N/A | 322 | N/A | 🟡 Medium
|  | Use Case Points (UCP) | N/A | 396.9 | N/A | 396.9 | N/A | 🟡 Medium
⚠️ RISK ADJUSTMENTS | [6 empty] | 🎯 RECOMMENDED ESTIMATE
Risk Factor | Level | % of Base | Impact (hrs) | Probability | Expected Impact |  | 414.8 hrs
Unclear Requirements | High | 10% | 41 | 60% | 24.6
New Technology / Tools | Medium | 5% | 21 | 40% | 8.4
Team Skill Gaps | Medium | 4% | 17 | 30% | 5.1 |  | 💡 WHY THIS ESTIMATE?
Integration Complexity | High | 6% | 25 | 50% | 12.5 |  | ✅ Average of PERT (409.2) & Three-Point (420.3)
3rd-Party Dependencies | Low | 3% | 12 | 20% | 2.4 |  | ✅ Both use same 21 requirements (O/M/P values)
Regulatory / Compliance | Medium | 5% | 21 | 30% | 6.3 |  | ✅ Reduces single-method estimation bias
Environment Instability | High | 7% | 29 | 50% | 14.5 |  | ✅ Represents balanced, defensible consensus
🔺 Total Risk Buffer (hrs) |  |  |  |  | 73.8 |  | ⚠️ + Risk Buffer (73.8 hrs): |  | 488.6 hrs
[7 empty] | 💰 Total QA Budget: |  | 407680.35
📘 LEGEND: How Impact (hrs) is Derived
Formula: Impact (hrs) = Recommended Estimate (414.8 hrs) × % of Base
⚡ Risk Level Definitions:
🔴 High | 6-10% of base estimate ¦ 50-60% probability ¦ Major impact on schedule/budget
🟡 Medium | 4-5% of base estimate ¦ 30-40% probability ¦ Moderate impact, manageable
🟢 Low | 2-3% of base estimate ¦ 10-20% probability ¦ Minor impact, easily mitigated
📊 Expected Impact Calculation:
Expected Impact = Impact (hrs) × Probability → Total Risk Buffer = Sum of all Expected Impacts
📊 WHY ESTIMATES DIFFER — STAKEHOLDER FAQ
Why does Story Points (372.5 hrs) show a lower estimate than PERT (409.2 hrs) and Three-Point (420.3 hrs)?
Technique | Estimate | Formula | Uncertainty | Best For | Why Different
PERT (Weighted) | 409.2 | (O+4M+P)/6 | ✅ Includes buffer | Waterfall/Hybrid | Weighted avg adds risk margin
Three-Point (Triangular) | 420.3 | (O+M+P)/3 | ✅ Includes buffer | Waterfall/Hybrid | Most conservative estimate
🃏 Story Points (Agile) | 372.5 | SP × Hrs/SP | ❌ NO buffer | Agile/Scrum | Direct conversion only
📐 Use Case Points (UCP) | 396.9 | UCP × 3 hrs | ✅ QA-specific factor | Waterfall/Hybrid | Now aligned with others!
💡 KEY INSIGHT: All Estimates Now Aligned
1️⃣ | Story Points use DIRECT conversion: 149 SP × 2.5 hrs/SP = 372.5 hrs — NO uncertainty buffer added.
2️⃣ | PERT & Three-Point use O/M/P ranges (229 / 398 / 634 hrs) — these methods INCLUDE uncertainty.
3️⃣ | The difference (~37-48 hrs) represents the RISK BUFFER that PERT/Three-Point automatically include.
4️⃣ | Story Points 372.5 hrs ≈ Most Likely (M) of 398 hrs — confirming alignment between methods.
🗣️ STAKEHOLDER TALKING POINT
The Story Points (372.5 hrs) is BASE effort. PERT (409.2) and Three-Point (420.3) include buffers. The ~42-hr difference (~11%) is the risk margin. Recommend 414.8 hrs.
📐 FORMULA COMPARISON
Story Points: | 149 SP x 2.5 | 372.5 hrs | No buffer
PERT: | (O+4M+P)/6 | 409.2 hrs | Weighted
Three-Point: | (O+M+P)/3 | 420.3 hrs | Conservative
Recommended: | Average | 414.8 hrs | Consensus

## ⚙️ Config
⚙️ PROJECT CONFIGURATION & TEAM SETUP
📋 PROJECT INFORMATION
| Project Name | Phoenix Platform Modernization | ← Fill in
| Release / Version | Release 3.0 | ← Fill in
| QA Lead | Jane Smith | ← Fill in
| QA Manager | Vishvambruth Javagal | ← Fill in
| Start Date | 2026-06-01 | YYYY-MM-DD
| End Date | 2026-09-30 | YYYY-MM-DD
| Working Hrs/Day | 8 | hrs
| Team Size (QA) | 6 | headcount
| Sprint Length | 2 | weeks
| QA Duration Wks | 17.3 | auto-calc
👥 QA TEAM ROSTER
| Name | Role | Skill Level | Rate ($/hr) | Sprint Allocation %
| Jane Smith | QA Lead | Senior | 95 | 100%
| Aisha Patel | Test Analyst | Mid | 70 | 100%
| Tom Reyes | Automation Eng (UI/API) | Senior | 90 | 90%
| Alex Kim | Mobile Automation Eng | Mid | 75 | 90%
| Carlos Vega | Performance Tester | Mid | 75 | 60%
| Lucy Chen | Junior Tester | Junior | 50 | 90%
💡 LEGEND: Cell Colours
📋 DATA TABLE - HEADERS
✏️ USER INPUT — fill these cells
🔢 FORMULA — auto-calculated
🔒 LABEL — do not edit

## 📊 PERT Estimation
📊 PERT ESTIMATION — REQUIREMENT-BASED (Single Source of Truth)
Formula: PERT = (O + 4M + P) / 6 ¦ Std Dev = (P - O) / 6 ¦ 95% CI = PERT ± 1.96 × σ
📋 REQUIREMENT-BASED PERT ESTIMATES (Linked to project requirements)
Module / Functionality | Requirement / User Story | Complexity | Optimistic (O) | Most Likely (M) | Pessimistic (P) | PERT Hrs | Std Dev (σ) | Lower 95% | Upper 95%
User Management | Registration & Login | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Password Reset Flow | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
Product Catalog | Browse & Search | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Product Detail Page | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Filter & Sort | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
Cart & Checkout | Add/Remove Cart Items | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
| Checkout Flow | 🔴 Complex | 20 | 40 | 64 | 40.6667 | 7.3333 | 26.2933 | 55.04
Payment | Order Confirmation | 🟢 Simple | 5 | 10 | 18 | 10.5 | 2.1667 | 6.2533 | 14.7467
| Credit Card Integration | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Refund/Cancellation | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
Reporting | Dashboard & Charts | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Export (CSV/PDF) | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
Notifications | Email/SMS Alerts | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
Admin Panel | User Management Admin | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Config & Settings | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
Performance/Security | Load & Stress Testing | 🔴 Complex | 24 | 48 | 72 | 48 | 8 | 32.32 | 63.68
| Security Penetration | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
Regression & Stabilization | Full Regression Suite | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Bug Fix Verification | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
UAT & Release Prep | UAT Support & Fixes | 🟡 Medium | 12 | 20 | 32 | 20.6667 | 3.3333 | 14.1333 | 27.2
| Release Sign-off Testing | 🟢 Simple | 7.5 | 12.5 | 20 | 12.9167 | 2.0833 | 8.8333 | 17
TOTALS |  |  | 229 | 398 | 634 | 409.1667 | 16.38 | 377.0618 | 441.2715
📌 SUMMARY — SINGLE PERT ESTIMATE (Used by Dashboard)
Total PERT Hours |  |  | Std Dev (σ) |  | Lower 95% CI |  | Upper 95% CI |  | Confidence
409.1667 |  |  | 16.38 |  | 377.0618 |  | 441.2715 |  | 🟢 High
💡 HOW O/M/P VALUES ARE DERIVED (Waterfall/Hybrid Approach)
In Waterfall/Hybrid projects, O/M/P are estimated directly based on requirement complexity, historical data, and expert judgment.
Estimate Type | Definition |  | How to Derive | Typical Factors | Example
Optimistic (O) | Best-case scenario |  | Ideal conditions: clear reqs, no blockers, experienced team | Perfect understanding, no defects, automation available | Login: 12 hrs
Most Likely (M) | Realistic scenario |  | Based on historical data; typical conditions | Average complexity, some clarifications, standard defects | Login: 20 hrs
Pessimistic (P) | Worst-case scenario |  | Account for risks: unclear reqs, new tech, rework | High complexity, multiple defect cycles, env issues | Login: 32 hrs
PERT Estimate | (O + 4M + P) / 6 |  | Weighted average; more weight to Most Likely | 4× weight on M, smooths extremes | (12+80+32)/6 = 20.7 hrs
📏 ESTIMATION GUIDELINES BY REQUIREMENT COMPLEXITY
Complexity | Characteristics |  | O (hrs) | M (hrs) | P (hrs) | Ratio (O:M:P)
🟢 Simple | Clear requirements, standard functionality |  | 4-8 | 8-16 | 16-24 | 1:2:3
🟡 Medium | Some integrations, moderate complexity |  | 8-16 | 16-32 | 32-48 | 1:2:3
🔴 Complex | Multiple integrations, new tech, high risk |  | 16-32 | 32-64 | 64-96 | 1:2:3
⚠️ PERT vs AGILE: WHEN TO USE EACH
Methodology | Best For |  | How to Estimate | Key Principle
📊 PERT (This Sheet) | Waterfall / Hybrid projects |  | Direct O/M/P hours based on req analysis & historical data | Absolute estimation in hours
🃏 Story Points (Agile) | Scrum / Kanban projects |  | Relative sizing using Fibonacci; convert via velocity | Relative estimation (not hours)
📝 NOTE: This sheet uses PERT for Waterfall/Hybrid projects. O/M/P values should be estimated directly based on requirement complexity

## 🔺 Three-Point
🔺 THREE-POINT ESTIMATION — REQUIREMENT-BASED (Triangular Method)
Triangular Formula: (O + M + P) / 3 ¦ Std Dev: (P - O) / 6 ¦ 95% CI = Estimate ± 1.96 × σ
📋 REQUIREMENT-BASED THREE-POINT ESTIMATES (Triangular Method)
Module / Functionality | Requirement / User Story | Complexity | Optimistic (O) | Most Likely (M) | Pessimistic (P) | Three-Point Est. | Std Dev
User Management | Registration & Login | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
User Management | Password Reset Flow | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
Product Catalog | Browse & Search | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Product Catalog | Product Detail Page | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Product Catalog | Filter & Sort | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
Cart & Checkout | Add/Remove Cart Items | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
Cart & Checkout | Checkout Flow | 🔴 Complex | 20 | 40 | 64 | 41.3333 | 7.3
Payment | Order Confirmation | 🟢 Simple | 5 | 10 | 18 | 11 | 2.2
Payment | Credit Card Integration | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Payment | Refund/Cancellation | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
Reporting | Dashboard & Charts | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Reporting | Export (CSV/PDF) | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
Notifications | Email/SMS Alerts | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Admin Panel | User Management Admin | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Admin Panel | Config & Settings | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
Performance/Security | Load & Stress Testing | 🔴 Complex | 24 | 48 | 72 | 48 | 8
Performance/Security | Security Penetration | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Regression & Stabilization | Full Regression Suite | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
Regression & Stabilization | Bug Fix Verification | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
UAT & Release Prep | UAT Support & Fixes | 🟡 Medium | 12 | 20 | 32 | 21.3333 | 3.3
UAT & Release Prep | Release Sign-off Testing | 🟢 Simple | 7.5 | 12.5 | 20 | 13.3333 | 2.1
TOTALS |  |  | 229 | 398 | 634 | 420.3333 | 16.3
📌 SUMMARY — THREE-POINT ESTIMATE (Triangular Method - Used by Dashboard)
Total Three-Point Hours |  |  |  | Std Dev (σ) |  | 95% Confidence Interval
420.3333 |  |  |  | 16.3 |  | 388.4 – 452.3
💡 THREE-POINT ESTIMATION METHOD EXPLAINED (Waterfall/Hybrid Approach)
Method | Formula | Description | Best For | When to Use
Triangular (Three-Point) | (O + M + P) / 3 | Equal weight to all estimates | Balanced uncertainty | When O, M, P equally reliable
📏 ESTIMATION GUIDELINES BY REQUIREMENT COMPLEXITY
Complexity | Characteristics | O (hrs) | M (hrs) | P (hrs) | Ratio (O:M:P)
🟢 Simple | Clear requirements, standard functionality | 4-8 | 8-16 | 16-24 | 1:2:3
🟡 Medium | Some integrations, moderate complexity | 8-16 | 16-32 | 32-48 | 1:2:3
🔴 Complex | Multiple integrations, new tech, high risk | 16-32 | 32-64 | 64-96 | 1:2:3

## 🃏 Story Points
🃏 STORY POINT ESTIMATION — AGILE / SCRUM
QA Hours = Story Points × Hours-per-Point (velocity) ¦ Fibonacci scale: 1, 2, 3, 5, 8, 13, 21
⚡ VELOCITY & CAPACITY SETTINGS
Avg. Velocity (SP/sprint) | 40 | ← Team historical average
Sprint Capacity (hrs) | 480 | ← Team size × hrs/day × sprint days
Hours per Story Point (QA) | 2.5 | ← QA hrs per SP (calibrate each project)
Number of Sprints Planned | 9 | ← Total planned sprints
📋 USER STORY ESTIMATES
📊 EPIC-LEVEL ESTIMATES
Epic Name | Story Points | Priority | Sprint | QA Hrs Est. | Status
Epic: User Management | 13 | High | Sprint 1 | 32.5 | Planned
Epic: Product Catalog | 21 | High | Sprint 2 | 52.5 | Planned
Epic: Cart & Checkout | 21 | Critical | Sprint 3 | 52.5 | Planned
Epic: Payment | 13 | Critical | Sprint 4 | 32.5 | Planned
Epic: Reporting | 13 | Medium | Sprint 5 | 32.5 | Planned
Epic: Notifications | 8 | Low | Sprint 6 | 20 | Planned
Epic: Admin Panel | 13 | Medium | Sprint 6 | 32.5 | Planned
Epic: Performance/Security | 21 | High | Sprint 7 | 52.5 | Planned
Epic: Regression & Stabilization | 13 | High | Sprint 8 | 32.5 | Planned
Epic: UAT & Release Prep | 13 | Critical | Sprint 9 | 32.5 | Planned
EPIC TOTALS | 149 |  |  | 372.5
📋 USER STORY BREAKDOWN (Must Equal Epic Totals)
Parent Epic | User Story | Story Points | Priority | Sprint | QA Hrs Est. | QA Hrs Actual | Variance | Status
User Management | Registration & Login | 8 | High | Sprint 1 | 20 |  |  | To Do
| Password Reset Flow | 5 | Medium | Sprint 1 | 12.5 |  |  | To Do
Product Catalog | Browse & Search | 8 | High | Sprint 2 | 20 |  |  | To Do
| Product Detail Page | 8 | High | Sprint 2 | 20 |  |  | To Do
| Filter & Sort | 5 | Medium | Sprint 2 | 12.5 |  |  | To Do
Cart & Checkout | Add/Remove Cart Items | 5 | Critical | Sprint 3 | 12.5 |  |  | To Do
| Checkout Flow | 13 | Critical | Sprint 3 | 32.5 |  |  | To Do
Payment | Order Confirmation | 3 | High | Sprint 4 | 7.5 |  |  | To Do
| Credit Card Integration | 8 | Critical | Sprint 4 | 20 |  |  | To Do
| Refund/Cancellation | 5 | High | Sprint 4 | 12.5 |  |  | To Do
Reporting | Dashboard & Charts | 8 | Medium | Sprint 5 | 20 |  |  | To Do
| Export (CSV/PDF) | 5 | Medium | Sprint 5 | 12.5 |  |  | To Do
Notifications | Email/SMS Alerts | 8 | Low | Sprint 6 | 20 |  |  | To Do
Admin Panel | User Management Admin | 8 | Medium | Sprint 6 | 20 |  |  | To Do
| Config & Settings | 5 | Medium | Sprint 6 | 12.5 |  |  | To Do
Performance/Security | Load & Stress Testing | 13 | High | Sprint 7 | 32.5 |  |  | To Do
| Security Penetration | 8 | High | Sprint 7 | 20 |  |  | To Do
Regression & Stabilization | Full Regression Suite | 8 | High | Sprint 8 | 20 |  |  | To Do
| Bug Fix Verification | 5 | Medium | Sprint 8 | 12.5 |  |  | To Do
UAT & Release Prep | UAT Support & Fixes | 8 | Critical | Sprint 9 | 20 |  |  | To Do
| Release Sign-off Testing | 5 | High | Sprint 9 | 12.5 |  |  | To Do
| USER STORY TOTALS | 149 |  |  | 372.5 | 0 | 0
✅ VALIDATION: Epic vs User Story Totals
Match Status: | ✅ MATCH | Epic SP: | 149 | Story SP: | 149
📊 CAPACITY vs ESTIMATE RECONCILIATION
Explains the gap between Story Point estimates and Sprint Capacity — for stakeholder discussions
Category | Hours | % of Capacity | Notes
📦 GROSS SPRINT CAPACITY
Total Available Capacity | 4320 | 100% | Sprint Capacity 480 hrs × 9 Sprints
OVERHEAD DEDUCTIONS from Gross Capacity
Meetings, Stand-ups, Reviews | 648 | 15% | Daily stand-ups, sprint reviews, planning
Test Environment Setup/Maint. | 432 | 10% | Environment prep, data setup
Documentation and Reporting | 216 | 5% | Test reports, status updates
Defect Triage and Retesting | 432 | 10% | Bug analysis, verification
Buffer/Contingency | 432 | 10% | Unplanned work, scope changes
Total Overhead | 2160 | 50% | Typical range: 40-60%
NET PRODUCTIVE CAPACITY
Available for Testing | 2160 | 50% | Gross Capacity minus Overhead
EFFORT ALLOCATION
Story Point Testing (Feature) | 372.5 | 17.2% | Direct testing from User Stories
Regression Testing (per sprint) | 540 | 25% | ~25% of net capacity for regression
Exploratory / Ad-hoc Testing | 324 | 15% | Risk-based, session-based testing
UAT Support | 216 | 10% | Supporting business users
Total Allocated Effort | 1452.5 | 67.2% | Should be <= Net Capacity
SUMMARY FOR STAKEHOLDERS
Gross Capacity (Total Available) | 4320 | hrs
Less: Overhead (50%) | 2160 | hrs
Net Productive Capacity | 2160 | hrs
Allocated Effort | 1452.5 | hrs
Utilization Rate | 67.2 | %
✅ Effort fits within Net Capacity — estimates are defensible!
📋 UTILIZATION RATE JUSTIFICATION (70.7% — Why This is Optimal)
Use this section to explain utilization rate to customers and stakeholders
📊 INDUSTRY BENCHMARK COMPARISON
Utilization Range | Assessment | Risk Level | Recommendation
90-100% | ❌ Unrealistic | Very High | No buffer for issues
80-90% | ⚠️ Aggressive | High | Risky if scope changes
70-80% | ✅ OPTIMAL | Low | Balanced & defensible
60-70% | ⚠️ Conservative | Medium | May indicate over-staffing
< 60% | ❌ Under-utilized | Low | Resource waste
🛡️ WHAT THE 29.3% BUFFER COVERS
Risk / Activity | Description | Typical Impact | Why Needed
Scope Creep | Requirements changes mid-sprint | 5-15% | Common in agile projects
Production Issues | Hotfixes, emergency testing | 5-10% | Unplanned but expected
Sick Leave / PTO | Unplanned team absences | 5-8% | Human resource reality
Knowledge Transfer | Onboarding, cross-training | 3-5% | Team sustainability
Process Improvements | Retrospectives, tooling | 2-5% | Continuous improvement
Learning Curve | New technology adoption | 3-8% | Innovation overhead
Collaboration | Ad-hoc dev/business support | 5-10% | Cross-team dependencies
Context Switching | Multi-tasking overhead | 10-15% | Industry standard loss
🗣️ KEY TALKING POINTS FOR STAKEHOLDERS
1️⃣ | "70-80% utilization is the industry standard for knowledge workers — studies show productive 'hands-on' time averages 60-70% of total hours."
2️⃣ | "The remaining 29.3% isn't wasted — it's intentional buffer for scope changes, production issues, and unplanned work that WILL occur."
3️⃣ | "Projects with 90%+ utilization consistently fail to meet deadlines because they have no capacity to absorb inevitable changes."
4️⃣ | "Our 70.7% utilization demonstrates responsible planning — we've accounted for real-world risks while maximizing productivity."
5️⃣ | "This buffer has already absorbed: meetings (15%), environment setup (10%), documentation (5%), defect triage (10%), and contingency (10%)."
✅ BOTTOM LINE FOR CUSTOMER
"Our 70.7% utilization rate represents a well-planned, risk-aware approach to QA resource allocation. We've allocated 1,272.5 hours of direct testing effort within 1,800 hours of net productive capacity. The 29.3% buffer ensures we can handle scope changes, production issues, and team availability challenges without impacting delivery timelines or quality. This is not under-utilization — it's responsible project management."
📊 YOUR PROJECT'S UTILIZATION METRICS (Auto-calculated)
Gross Capacity: | 4320 hrs
Net Productive Capacity: | 2160 hrs
Allocated Effort: | 1452.5 hrs
Utilization Rate: | 67.2%
Buffer Remaining: | 32.8%

## 🔍 Analogy
🔍 ANALOGY-BASED ESTIMATION
Compare current project to completed reference projects. Adjust using complexity factor.
📚 REFERENCE PROJECT LIBRARY
Reference Project | QA Hours Actual | Complexity Factor | Adj. Hrs | Similarity %
Project Alpha — E-Commerce v1 | 320 | 1 | 320 | 85%
Project Beta — Portal Upgrade | 240 | 0.9 | 216 | 70%
Project Gamma — API Integration | 180 | 1.1 | 198 | 60%
Project Delta — Mobile App QA | 280 | 1.2 | 336 | 75%
Project Epsilon — Legacy Mig. | 400 | 1.3 | 520 | 50%
Project Zeta — Data Platform | 350 | 1.1 | 385 | 65%
🎯 WEIGHTED ANALOGY ESTIMATE
Weighted Avg QA Hours |  |  | 322 | 🟡 Medium

## 📐 UCP
📐 USE CASE POINT (UCP) ESTIMATION
UCP = (UUCW + UAW) × TCF × ECF ¦ QA Hrs = UCP × Productivity Factor
📊 USE CASE COMPLEXITY WEIGHTS
Use Case Complexity | Simple (≤3 txns) | Average (4-7) | Complex (>7)
UUCW Weight | 5 | 10 | 15
Actor Complexity | Simple (API) | Average (UI) | Complex (other)
UAW Weight | 1 | 2 | 3
🧩 USE CASE INVENTORY
Use Case Name | Complexity | UUCW | Actors | UAW | Total UC Points
Login & Authentication | Simple | 5 | Simple | 1 | 6
User Registration | Simple | 5 | Average | 2 | 7
Browse Product Catalog | Average | 10 | Average | 2 | 12
Product Search & Filter | Average | 10 | Average | 2 | 12
Manage Shopping Cart | Average | 10 | Complex | 3 | 13
Checkout Process | Complex | 15 | Complex | 3 | 18
Payment Processing | Complex | 15 | Complex | 3 | 18
Order Tracking | Average | 10 | Average | 2 | 12
Returns & Refunds | Average | 10 | Average | 2 | 12
Generate Sales Reports | Complex | 15 | Average | 2 | 17
Admin: User Management | Average | 10 | Simple | 1 | 11
Admin: Product Management | Average | 10 | Simple | 1 | 11
Send Notifications | Simple | 5 | Average | 2 | 7
View Analytics Dashboard | Complex | 15 | Average | 2 | 17
TOTALS |  | 145 |  | 28 | 173
⚙️ TECHNICAL & ENV. COMPLEXITY FACTORS
TCF (Technical Complexity) | 0.85 | 0.6–1.3 range; lower = more complex
ECF (Environment Complexity) | 0.9 | 0.5–1.4 range; lower = less stable env
UCP (Adjusted) | 132.3 | auto-calc
QA Productivity Factor (hrs/UCP) | 3 | ← QA-specific: 2-5 hrs/UCP (Dev uses 15-25)
Total QA Hrs (UCP Method) | 396.9 | auto-calc
💡 WHY UCP ESTIMATE DIFFERS & HOW TO CALIBRATE
UCP was originally designed for DEVELOPMENT effort. For QA-only estimation, use a lower productivity factor.
📊 PRODUCTIVITY FACTOR COMPARISON
Estimation Context | Factor Range | Typical Value | Your UCP (132.3) | Result
Development (Full SDLC) | 15-25 hrs/UCP | 20 hrs/UCP | 132.3 × 20 | 2,646 hrs
QA Only (Recommended) ✅ | 2-5 hrs/UCP | 3 hrs/UCP | 132.3 × 3 | 396.9 hrs
QA + Automation Setup | 5-8 hrs/UCP | 6 hrs/UCP | 132.3 × 6 | 793.8 hrs
QA + Test Design | 8-12 hrs/UCP | 10 hrs/UCP | 132.3 × 10 | 1,323 hrs
🔑 KEY INSIGHT: Aligning UCP with Other Estimates
Using QA-specific factor (3 hrs/UCP): 132.3 × 3 = 396.9 hrs
This aligns with PERT (409.2 hrs) & Three-Point (420.3 hrs) ✅
🗣️ STAKEHOLDER TALKING POINT
"The UCP method shows different results based on the productivity factor. For QA-only scope, we use
3 hrs/UCP (industry standard), giving ~397 hrs — consistent with PERT and Three-Point estimates."
📐 FORMULA REFERENCE
UCP = (UUCW + UAW) × TCF × ECF = (145 + 28) × 0.85 × 0.90 = 132.3
QA Hours = UCP × QA Factor = 132.3 × 3.0 = 396.9 hours

## 📝 Test Planning
📝 TEST PLANNING & TEST CASE ESTIMATION
Test Cases = Requirements × Test-to-Req Ratio ¦ Hours = Test Cases × hrs per case
74
⚙️ PLANNING PARAMETERS
Total Requirements (User Stories) | 21 | ← count from backlog
Test-to-Req Ratio | 3.5 | ← avg test cases per requirement
Hrs per Test Case (Design) | 1 | ← estimation standard
Hrs per Test Case (Execution) | 1 | ← estimation standard
Hrs per Test Case (Regression) | 0.5 | ← per regression cycle
Number of Regression Cycles | 3 | ← sprints / releases
Review & Rework Buffer (%) | 0.5 | ← overhead factor
📊 ESTIMATED OUTPUTS
Estimated Test Cases | 74
Test Design Hours | 74
Test Execution Hours | 74
Regression Hours (total) | 111
Sub-Total QA Hours | 259
Review & Rework (buffer) | 129.5
TOTAL Test Planning Hours | 388.5

## 💰 Budget Planner
💰 QA BUDGET PLANNER
Budget = (Team Hours × Hourly Rates) + Tools + Training + Infrastructure + Contingency
👥 LABOR COST BREAKDOWN
Team Member | Role | Hrs/Sprint | No. Sprints | Total Hrs | $/hr | Labor Cost | Benefits (30%) | Total Cost
Jane Smith | QA Lead | 80 | 9 | 720 | 95 | 68400 | 20520 | 88920
Aisha Patel | Test Analyst | 80 | 9 | 720 | 70 | 50400 | 15120 | 65520
Tom Reyes | Automation Eng (UI/API) | 72 | 8 | 576 | 90 | 51840 | 15552 | 67392
Alex Kim | Mobile Automation Eng | 72 | 8 | 576 | 75 | 43200 | 12960 | 56160
Carlos Vega | Performance Tester | 48 | 3 | 144 | 75 | 10800 | 3240 | 14040
Lucy Chen | Junior Tester | 72 | 8 | 576 | 50 | 28800 | 8640 | 37440
LABOR TOTALS |  | 424 | Number of Sprints: 9 | 3312 | 76 | 253440 | 76032 | 329472
🛠️ TOOLS, INFRASTRUCTURE & OTHER COSTS
Cost Category | Description | Unit Cost | Quantity | Frequency | Total Cost
Test Automation Tools | Selenium/Playwright license | 200 | 3 | 12 | 7200
Test Mgmt Tool | Jira/TestRail subscription | 50 | 5 | 6 | 1500
Performance Tools | JMeter / LoadRunner | 300 | 1 | 1 | 300
Security Tools | OWASP ZAP / BurpSuite | 400 | 1 | 1 | 400
CI/CD Integration | Pipeline setup & maint. | 150 | 1 | 6 | 900
Dev/QA Environment | Cloud infra (AWS/Azure) | 500 | 1 | 6 | 3000
Training | QA skills & tool training | 800 | 2 | 1 | 1600
Travel & Expenses | Onsite visits / stakeholder | 500 | 2 | 1 | 1000
Miscellaneous | 10% buffer for unknowns | 0 | 1 | 1 | 1590
TOTAL NON-LABOR COSTS |  |  |  |  | 17490
💰 TOTAL QA BUDGET | [7 empty] | 346962
⚠️ + Contingency Buffer (recommended 15-20%) | [7 empty] | 60718.35
✅ FINAL RECOMMENDED QA BUDGET | [7 empty] | GRAND TOTAL (with contingency)
407680.35
0

## 📅 Sprint Resource Plan
📅 SPRINT-BY-SPRINT RESOURCE ALLOCATION PLAN
Plan QA headcount and hours per sprint; monitor actuals vs. estimates
📋 SPRINT ALLOCATION MATRIX
Sprint | Planned Hrs | Actual Hrs | Variance | Variance % | Features In Scope | Test Cases | Pass Rate % | Bugs Found | Status | Team Members Active
Sprint 1 | 160 | 80 | 80 | 50% |  |  |  |  | ⚠️ Under Utilized | QA Lead
Sprint 2 | 376 | 376 | 0 | 0% |  |  |  |  | ✅ Utilized | QA Lead, Test Analyst, Automation, Mobile, Manual Tester
Sprint 3 | 376 | 304 | 72 | 19.15% |  |  |  |  | ⚠️ Under Utilized | QA Lead, Test Analyst, Automation, Manual Tester
Sprint 4 | 376 | 304 | 72 | 19.15% |  |  |  |  | ⚠️ Under Utilized | QA Lead, Test Analyst, Automation, Manual Tester
Sprint 5 | 376 | 376 | 0 | 0% |  |  |  |  | ✅ Utilized | QA Lead, Test Analyst, Automation, Mobile, Manual Tester
Sprint 6 | 376 | 376 | 0 | 0% |  |  |  |  | ✅ Utilized | QA Lead, Test Analyst, Automation, Mobile, Manual Tester
Sprint 7 | 424 | 424 | 0 | 0% |  |  |  |  | ✅ Utilized | QA Lead, Test Analyst, Automation, Mobile, Manual Tester, Perf
Sprint 8 | 424 | 424 | 0 | 0% |  |  |  |  | ✅ Utilized | QA Lead, Test Analyst, Automation, Mobile, Manual Tester, Perf
Sprint 9 | 424 | 424 | 0 | 0% |  |  |  |  | ✅ Utilized | QA Lead, Test Analyst, Automation, Mobile, Manual Tester, Perf
TOTALS | 3312 | 3088 | 224 | 6.763%
👥 TEAM RAMP-UP SCHEDULE
Team Member | Role | Joins Sprint | Ends Sprint | Sprints Active | Join # | Allocation % | Hrs/Sprint
Jane Smith | QA Lead | Sprint 1 | Sprint 9 | 9 (Full project) | 1 | 100% | 80
Aisha Patel | Test Analyst | Sprint 1 | Sprint 9 | 9 (Full project) | 1 | 100% | 80
Tom Reyes | Automation Eng (UI/API) | Sprint 2 | Sprint 9 | 8 (After Sprint 1) | 2 | 90% | 72
Alex Kim | Mobile Automation Eng | Sprint 2 | Sprint 9 | 8 (After Sprint 1) | 2 | 90% | 72
Carlos Vega | Performance Tester | Sprint 7 | Sprint 9 | 3 (Final sprints) | 7 | 60% | 48
Lucy Chen | Manual Tester | Sprint 2 | Sprint 9 | 8 (After Sprint 1) | 2 | 90% | 72
📐 FORMULA EXPLANATION
Planned Hrs Formula: | =SUMPRODUCT(($G$21:$G$26<=SprintNum)*$I$21:$I$26)
Actual Hrs Formula: | =ROUND(Planned*(1-Variance%),0)
Variance Formula: | =Planned Hrs - Actual Hrs
# QA Formula: | =SUMPRODUCT(($G$21:$G$26<=SprintNum)*1)
💡 TO MODIFY: Change Join # or Allocation % in the Team Ramp-Up table above. All calculations will auto-update!

## 📖 How to Use
📖 HOW TO USE — QA ESTIMATION TEMPLATE
🟣 STEP 1 — Configure Your Project | ⚙️ Config sheet
Fill in Project Name, Release, QA Lead, Team roster with roles, skill levels, hourly rates and sprint allocation.
🟣 STEP 2 — PERT Phase Estimation | 📊 PERT Estimation sheet
Enter Optimistic, Most Likely and Pessimistic hours for each QA phase. PERT and Std Dev calculate automatically.
🟣 STEP 3 — Feature-Level Three-Point | 🔺 Three-Point sheet
Enter O/M/P hours for each feature or user story. Both PERT and Triangular averages are computed.
🟣 STEP 4 — Story Points (Agile) | 🃏 Story Points sheet
Assign story points per epic/story. Set velocity and hours-per-point. QA hours auto-calculate.
🟣 STEP 5 — Analogy Estimation | 🔍 Analogy sheet
Enter reference (past) projects with actual QA hours, complexity factors and similarity %. Weighted estimate is computed.
🟣 STEP 6 — Use Case Points | 📐 UCP sheet
Log use cases with complexity. Set TCF, ECF and productivity factor. Total QA hours are estimated.
🟣 STEP 7 — Test Case Planning | 📝 Test Planning sheet
Set requirements count, test-to-req ratio and hrs/case. Total design, execution and regression hours auto-calculate.
🟣 STEP 8 — Budget Planning | 💰 Budget Planner sheet
Labor costs pull from Config. Add tool, infra and training costs. Final budget with contingency auto-totals.
🟣 STEP 9 — Risk Buffer | 📋 Dashboard → Risk table
Adjust risk probability and impact on the Dashboard. Total risk buffer adds to recommended estimate.
🟣 STEP 10 — Sprint Planning | 📅 Sprint Resource Plan sheet
Enter planned hours per sprint and assigned testers. As actuals come in, variance and status update automatically.
🟣 STEP 11 — Review Dashboard | 📋 Estimation Dashboard
The dashboard aggregates all techniques. Compare side-by-side and use PERT as the primary recommended estimate.
💡 COLOUR CODE | Dark Green cells = User Input
Dark Blue-Purple = Formula (do not edit) ¦ Purple sections = Section headers
💡 BEST PRACTICE | Use 2–3 techniques and compare
For new projects: PERT + Story Points. For similar past projects: Analogy. For requirement-heavy: UCP.
💡 CONFIDENCE | 🟢 High < 10% CV ¦ 🟡 Medium 10–20% ¦ 🔴 Low > 20%
CV = Std Dev / PERT Estimate. Lower is better. Aim for High on critical projects.